## 2024-05-27
Pacific Restoration Group, Inc.
222222 Project Beta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | pounds | cubic yards | tons | acres | tons | gallons | rolls | acres | ls
| 2024-05-27 | 033: 533.6379
TOTAL |  | 033: 533.6379

## 2024-05-26
Pacific Restoration Group, Inc.
222222 Project Beta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | pounds | cubic yards | tons | acres | tons | gallons | rolls | acres | ls
| 2024-05-20 | 2: 486.7277
| 2024-05-22 | 5: 122.2543
| 2024-05-24 | 033: 102.9421
| 2024-05-26 | 1: 70.7521; 2: 12.0712; 030: 41.3341; 032: 104.1423
TOTAL |  | 70.7521 | 498.7989 |  | 122.2543 |  | 41.3341 |  | 104.1423 | 102.9421

## 2024-05-19
Pacific Restoration Group, Inc.
222222 Project Beta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | pounds | cubic yards | tons | acres | tons | gallons | rolls | acres | ls
| 2024-05-16 | 1: 286.115; 032: 783.99
| 2024-05-18 | 032: 108.5537
| 2024-05-19 | 5: 215.5556
TOTAL |  | 1: 286.115; 5: 215.5556; 032: 892.5436

## 2024-05-12
Pacific Restoration Group, Inc.
222222 Project Beta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | pounds | cubic yards | tons | acres | tons | gallons | rolls | acres | ls
| 2024-05-06 | 2: 111.0065
| 2024-05-07 | 031: 54.693
| 2024-05-10 | 033: 277.5038
| 2024-05-11 | 029: 402.0312
TOTAL |  | 2: 111.0065; 029: 402.0312; 031: 54.693; 033: 277.5038

## 2024-05-05
Pacific Restoration Group, Inc.
222222 Project Beta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | pounds | cubic yards | tons | acres | tons | gallons | rolls | acres | ls
| 2024-04-29 | 030: 37.8009
| 2024-05-04 | 2: 13.6667
| 2024-05-05 | 2: 613.5962
TOTAL |  | 2: 627.2629; 030: 37.8009

## 2024-04-28
Pacific Restoration Group, Inc.
222222 Project Beta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | pounds | cubic yards | tons | acres | tons | gallons | rolls | acres | ls
| 2024-04-22 | 1: 169.8085
| 2024-04-24 | 031: 346.7518; 032: 2.343; 033: 85.018
| 2024-04-25 | 029: 17.9843
TOTAL |  | 1: 169.8085; 029: 17.9843; 031: 346.7518; 032: 2.343; 033: 85.018

## 2024-04-21
Pacific Restoration Group, Inc.
222222 Project Beta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | pounds | cubic yards | tons | acres | tons | gallons | rolls | acres | ls
| 2024-04-15 | 031: 420.4425
| 2024-04-16 | 033: 38.5836
| 2024-04-20 | 4: 341.6255; 5: 4.4124; 033: 196.3587
TOTAL |  | 4: 341.6255; 5: 4.4124; 031: 420.4425; 033: 234.9423

## 2024-04-14
Pacific Restoration Group, Inc.
222222 Project Beta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | pounds | cubic yards | tons | acres | tons | gallons | rolls | acres | ls
| 2024-04-09 | 029: 207.1751
| 2024-04-13 | 4: 104.5053; 030: 220.6756
| 2024-04-14 | 4: 448.5193; 032: 124.7201; 033: 8.3042
TOTAL |  | 4: 553.0246; 029: 207.1751; 030: 220.6756; 032: 124.7201; 033: 8.3042

## 2024-04-07
Pacific Restoration Group, Inc.
222222 Project Beta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | pounds | cubic yards | tons | acres | tons | gallons | rolls | acres | ls
| 2024-04-05 | 1: 177.8975
TOTAL |  | 1: 177.8975

## 2024-03-31
Pacific Restoration Group, Inc.
222222 Project Beta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | pounds | cubic yards | tons | acres | tons | gallons | rolls | acres | ls
| 2024-03-25 | 2: 2.8433
| 2024-03-27 | 4: 195.0419
| 2024-03-30 | 5: 217.4154
TOTAL |  | 2: 2.8433; 4: 195.0419; 5: 217.4154

## 2024-03-24
Pacific Restoration Group, Inc.
222222 Project Beta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | pounds | cubic yards | tons | acres | tons | gallons | rolls | acres | ls
| 2024-03-18 | 031: 489.1264
| 2024-03-23 | 032: 125.9965
TOTAL |  | 031: 489.1264; 032: 125.9965

## 2024-03-17
Pacific Restoration Group, Inc.
222222 Project Beta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | pounds | cubic yards | tons | acres | tons | gallons | rolls | acres | ls
| 2024-03-14 | 1: 2.3999
| 2024-03-17 | 4: 118.4833
TOTAL |  | 1: 2.3999; 4: 118.4833

## 2024-03-10
Pacific Restoration Group, Inc.
222222 Project Beta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | pounds | cubic yards | tons | acres | tons | gallons | rolls | acres | ls
| 2024-03-04 | 030: 33.7755
| 2024-03-06 | 030: 467.4593
| 2024-03-07 | 2: 364.5012
| 2024-03-09 | 030: 12.9234
| 2024-03-10 | 4: 271.8893; 032: 8.6326
TOTAL |  | 2: 364.5012; 4: 271.8893; 030: 514.1583; 032: 8.6326

## 2024-03-03
Pacific Restoration Group, Inc.
222222 Project Beta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | pounds | cubic yards | tons | acres | tons | gallons | rolls | acres | ls
| 2024-02-27 | 1: 400.5736
| 2024-02-29 | 029: 379.7083
| 2024-03-02 | 1: 291.9515
| 2024-03-03 | 032: 1.9987
TOTAL |  | 1: 692.5251; 029: 379.7083; 032: 1.9987

## 2024-02-25
Pacific Restoration Group, Inc.
222222 Project Beta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | pounds | cubic yards | tons | acres | tons | gallons | rolls | acres | ls
| 2024-02-21 | 029: 668.0913; 031: 14.3106
| 2024-02-22 | 1: 46.6524; 2: 603.0352; 033: 327.173
| 2024-02-24 | 1: 384.8378
| 2024-02-25 | 031: 0.97995
TOTAL |  | 1: 431.4902; 2: 603.0352; 029: 668.0913; 031: 15.2906; 033: 327.173

## 2024-02-18
Pacific Restoration Group, Inc.
222222 Project Beta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | pounds | cubic yards | tons | acres | tons | gallons | rolls | acres | ls
| 2024-02-12 | 1: 216.6746; 2: 102.9153
| 2024-02-13 | 033: 97.6864
| 2024-02-16 | 2: 91.2467
| 2024-02-17 | 1: 186.3709
| 2024-02-18 | 4: 62.6837
TOTAL |  | 1: 403.0456; 2: 194.162; 4: 62.6837; 033: 97.6864

## 2024-02-11
Pacific Restoration Group, Inc.
222222 Project Beta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | pounds | cubic yards | tons | acres | tons | gallons | rolls | acres | ls
| 2024-02-05 | 031: 382.7204
| 2024-02-07 | 2: 116.9265
| 2024-02-11 | 030: 138.4988
TOTAL |  | 2: 116.9265; 030: 138.4988; 031: 382.7204

## 2024-02-04
Pacific Restoration Group, Inc.
222222 Project Beta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | pounds | cubic yards | tons | acres | tons | gallons | rolls | acres | ls
| 2024-01-29 | 030: 190.6471
| 2024-01-30 | 031: 143.1972
| 2024-02-02 | 4: 349.55
| 2024-02-03 | 1: 27.2826
TOTAL |  | 1: 27.2826; 4: 349.55; 030: 190.6471; 031: 143.1972

## 2024-01-28
Pacific Restoration Group, Inc.
222222 Project Beta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | pounds | cubic yards | tons | acres | tons | gallons | rolls | acres | ls
| 2024-01-23 | 033: 76.6448
| 2024-01-24 | 1: 128.6444
| 2024-01-26 | 5: 80.7131
| 2024-01-27 | 031: 422.7984
TOTAL |  | 1: 128.6444; 5: 80.7131; 031: 422.7984; 033: 76.6448

## 2024-01-21
Pacific Restoration Group, Inc.
222222 Project Beta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | pounds | cubic yards | tons | acres | tons | gallons | rolls | acres | ls
| 2024-01-15 | 032: 161.5767
TOTAL |  | 032: 161.5767

## 2024-01-14
Pacific Restoration Group, Inc.
222222 Project Beta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | pounds | cubic yards | tons | acres | tons | gallons | rolls | acres | ls
| 2024-01-08 | 029: 257.7886
| 2024-01-09 | 030: 426.1479
| 2024-01-10 | 1: 538.9624; 032: 276.1772
| 2024-01-11 | 2: 5.7326; 029: 72.2019; 033: 901.5582
| 2024-01-12 | 2: 35.7781; 033: 438.4995
| 2024-01-13 | 4: 171.269; 030: 491.5565
| 2024-01-14 | 030: 857.3993
TOTAL |  | 538.9624 | 41.5107 | 171.269 |  | 329.9905 | 1775.1037 |  | 276.1772 | 1340.0578

## 2024-01-07
Pacific Restoration Group, Inc.
222222 Project Beta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | pounds | cubic yards | tons | acres | tons | gallons | rolls | acres | ls
| 2024-01-01 | 2: 339.3461; 4: 533.739; 031: 46.3594
| 2024-01-03 | 1: 135.9017
| 2024-01-04 | 5: 137.2719
| 2024-01-06 | 1: 217.8275; 5: 513.9138
TOTAL |  | 1: 353.7292; 2: 339.3461; 4: 533.739; 5: 651.1856; 031: 46.3594