## 05-30-24
Pacific Restoration Group, Inc.
333333 Project Alpha
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | feet | meters | meters | gallons | rolls | feet | bags | bags | tons
| 2024-05-28 | 033: 1.2388
| 2024-05-29 | 030: 287.7685
| 2024-05-30 | 4: 900.5584
TOTAL |  | 4: 900.5584; 030: 287.7685; 033: 1.2388

## 05-27-24
Pacific Restoration Group, Inc.
333333 Project Alpha
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | feet | meters | meters | gallons | rolls | feet | bags | bags | tons
| 2024-05-21 | 032: 11.8486
| 2024-05-22 | 4: 704.403
| 2024-05-23 | 033: 198.3229
| 2024-05-25 | 032: 0.16562
TOTAL |  | 4: 704.403; 032: 12.0142; 033: 198.3229

## 05-20-24
Pacific Restoration Group, Inc.
333333 Project Alpha
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | feet | meters | meters | gallons | rolls | feet | bags | bags | tons
| 2024-05-16 | 031: 715.4882; 033: 100.946
| 2024-05-19 | 4: 302.1445; 5: 80.6774
TOTAL |  | 4: 302.1445; 5: 80.6774; 031: 715.4882; 033: 100.946

## 05-13-24
Pacific Restoration Group, Inc.
333333 Project Alpha
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | feet | meters | meters | gallons | rolls | feet | bags | bags | tons
| 2024-05-11 | 1: 130.3201
| 2024-05-12 | 029: 111.6742
| 2024-05-13 | 2: 400.2575
TOTAL |  | 1: 130.3201; 2: 400.2575; 029: 111.6742

## 05-06-24
Pacific Restoration Group, Inc.
333333 Project Alpha
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | feet | meters | meters | gallons | rolls | feet | bags | bags | tons
| 2024-04-30 | 030: 17.2972
| 2024-05-02 | 030: 120.5152
| 2024-05-03 | 2: 132.7202; 4: 347.1157
| 2024-05-04 | 029: 57.4833; 032: 99.711
| 2024-05-05 | 031: 57.214
TOTAL |  |  | 132.7202 | 347.1157 |  | 57.4833 | 137.8124 | 57.214 | 99.711

## 04-29-24
Pacific Restoration Group, Inc.
333333 Project Alpha
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | feet | meters | meters | gallons | rolls | feet | bags | bags | tons
| 2024-04-25 | 032: 108.5417; 033: 416.6739
| 2024-04-26 | 033: 5.7486
| 2024-04-27 | 5: 288.4005
| 2024-04-28 | 029: 16.2541; 033: 141.1348
TOTAL |  | 5: 288.4005; 029: 16.2541; 032: 108.5417; 033: 563.5572

## 04-22-24
Pacific Restoration Group, Inc.
333333 Project Alpha
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | feet | meters | meters | gallons | rolls | feet | bags | bags | tons
| 2024-04-16 | 1: 30.2795
| 2024-04-18 | 1: 521.2475
| 2024-04-19 | 2: 306.9141; 033: 225.7898
| 2024-04-20 | 030: 449.7467
| 2024-04-21 | 031: 251.5043
| 2024-04-22 | 033: 34.8989
TOTAL |  | 1: 551.527; 2: 306.9141; 030: 449.7467; 031: 251.5043; 033: 260.6887

## 04-15-24
Pacific Restoration Group, Inc.
333333 Project Alpha
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | feet | meters | meters | gallons | rolls | feet | bags | bags | tons
| 2024-04-09 | 029: 95.5084; 031: 340.0274
| 2024-04-13 | 029: 2.3364
TOTAL |  | 029: 97.8449; 031: 340.0274

## 04-08-24
Pacific Restoration Group, Inc.
333333 Project Alpha
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | feet | meters | meters | gallons | rolls | feet | bags | bags | tons
| 2024-04-02 | 5: 113.3815; 029: 170.7801; 033: 176.0898
| 2024-04-03 | 029: 35.8223; 031: 63.4488
| 2024-04-04 | 033: 44.126
| 2024-04-06 | 5: 329.9552
TOTAL |  | 5: 443.3367; 029: 206.6024; 031: 63.4488; 033: 220.2158

## 04-01-24
Pacific Restoration Group, Inc.
333333 Project Alpha
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | feet | meters | meters | gallons | rolls | feet | bags | bags | tons
| 2024-03-28 | 4: 815.486
| 2024-03-29 | 032: 91.7012
| 2024-03-31 | 1: 578.5486
TOTAL |  | 1: 578.5486; 4: 815.486; 032: 91.7012

## 03-25-24
Pacific Restoration Group, Inc.
333333 Project Alpha
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | feet | meters | meters | gallons | rolls | feet | bags | bags | tons
| 2024-03-19 | 032: 628.662
| 2024-03-21 | 031: 328.6102; 032: 515.7366
| 2024-03-22 | 033: 490.5684
| 2024-03-23 | 5: 706.8246
| 2024-03-24 | 5: 315.9518
TOTAL |  | 5: 1022.7763; 031: 328.6102; 032: 1144.3986; 033: 490.5684

## 03-18-24
Pacific Restoration Group, Inc.
333333 Project Alpha
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | feet | meters | meters | gallons | rolls | feet | bags | bags | tons
| 2024-03-12 | 1: 66.8723
| 2024-03-13 | 5: 437.76; 031: 607.8094
| 2024-03-14 | 031: 4.3972; 032: 32.1399
| 2024-03-17 | 029: 124.7896
| 2024-03-18 | 1: 214.5463
TOTAL |  | 1: 281.4186; 5: 437.76; 029: 124.7896; 031: 612.2067; 032: 32.1399

## 03-11-24
Pacific Restoration Group, Inc.
333333 Project Alpha
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | feet | meters | meters | gallons | rolls | feet | bags | bags | tons
| 2024-03-08 | 030: 233.3246; 033: 139.8629
TOTAL |  | 030: 233.3246; 033: 139.8629

## 03-04-24
Pacific Restoration Group, Inc.
333333 Project Alpha
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | feet | meters | meters | gallons | rolls | feet | bags | bags | tons
| 2024-02-29 | 2: 108.8184
TOTAL |  | 2: 108.8184

## 02-26-24
Pacific Restoration Group, Inc.
333333 Project Alpha
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | feet | meters | meters | gallons | rolls | feet | bags | bags | tons
| 2024-02-22 | 5: 803.9729; 032: 64.4902
| 2024-02-24 | 2: 26.4896
TOTAL |  | 2: 26.4896; 5: 803.9729; 032: 64.4902

## 02-19-24
Pacific Restoration Group, Inc.
333333 Project Alpha
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | feet | meters | meters | gallons | rolls | feet | bags | bags | tons
| 2024-02-13 | 029: 382.9267
| 2024-02-14 | 029: 222.0192; 030: 245.7708
| 2024-02-15 | 033: 254.3718
| 2024-02-16 | 2: 135.5725
| 2024-02-17 | 1: 260.1606
| 2024-02-18 | 2: 23.2519; 033: 152.5023
| 2024-02-19 | 4: 135.1063
TOTAL |  | 260.1606 | 158.8244 | 135.1063 |  | 604.9459 | 245.7708 |  |  | 406.8741

## 02-12-24
Pacific Restoration Group, Inc.
333333 Project Alpha
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | feet | meters | meters | gallons | rolls | feet | bags | bags | tons
| 2024-02-08 | 1: 64.9002
| 2024-02-09 | 029: 545.9447; 031: 116.4642
| 2024-02-10 | 2: 692.8553; 033: 166.4434
| 2024-02-12 | 4: 72.1931; 5: 19.6988
TOTAL |  | 64.9002 | 692.8553 | 72.1931 | 19.6988 | 545.9447 |  | 116.4642 |  | 166.4434

## 02-05-24
Pacific Restoration Group, Inc.
333333 Project Alpha
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | feet | meters | meters | gallons | rolls | feet | bags | bags | tons
| 2024-01-31 | 032: 363.5022
| 2024-02-01 | 1: 835.1413
| 2024-02-02 | 1: 68.2125
TOTAL |  | 1: 903.3538; 032: 363.5022

## 01-29-24
Pacific Restoration Group, Inc.
333333 Project Alpha
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | feet | meters | meters | gallons | rolls | feet | bags | bags | tons
| 2024-01-24 | 4: 122.5497
| 2024-01-26 | 032: 460.6155
| 2024-01-27 | 032: 396.1033
TOTAL |  | 4: 122.5497; 032: 856.7187

## 01-22-24
Pacific Restoration Group, Inc.
333333 Project Alpha
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | feet | meters | meters | gallons | rolls | feet | bags | bags | tons
| 2024-01-18 | 030: 36.1525
| 2024-01-20 | 1: 54.6776
| 2024-01-21 | 029: 21.7924
TOTAL |  | 1: 54.6776; 029: 21.7924; 030: 36.1525

## 01-15-24
Pacific Restoration Group, Inc.
333333 Project Alpha
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | feet | meters | meters | gallons | rolls | feet | bags | bags | tons
| 2024-01-09 | 029: 154.8114
| 2024-01-14 | 031: 115.277
TOTAL |  | 029: 154.8114; 031: 115.277

## 01-08-24
Pacific Restoration Group, Inc.
333333 Project Alpha
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | feet | meters | meters | gallons | rolls | feet | bags | bags | tons
| 2024-01-02 | 2: 47.1462
| 2024-01-03 | 031: 341.7367
| 2024-01-05 | 2: 709.7745; 030: 243.8932
| 2024-01-06 | 1: 56.8109
TOTAL |  | 1: 56.8109; 2: 756.9207; 030: 243.8932; 031: 341.7367