## 2024-05-29
Pacific Restoration Group, Inc.
333333 Project Beta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | feet | ls | cubic yards | rolls | rolls | feet | feet | acres | ls
| 2024-05-27 | 033: 504.842
| 2024-05-29 | 2: 119.6735; 5: 5.3784; 030: 334.4498
TOTAL |  | 2: 119.6735; 5: 5.3784; 030: 334.4498; 033: 504.842

## 2024-05-26
Pacific Restoration Group, Inc.
333333 Project Beta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | feet | ls | cubic yards | rolls | rolls | feet | feet | acres | ls
| 2024-05-21 | 4: 65.8258
| 2024-05-22 | 029: 293.2867
| 2024-05-24 | 4: 104.5516; 029: 109.9335
| 2024-05-26 | 5: 219.6538; 029: 349.8878
TOTAL |  | 4: 170.3774; 5: 219.6538; 029: 753.108

## 2024-05-19
Pacific Restoration Group, Inc.
333333 Project Beta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | feet | ls | cubic yards | rolls | rolls | feet | feet | acres | ls
| 2024-05-14 | 4: 95.9855; 029: 250.6017; 031: 399.8887
| 2024-05-15 | 033: 30.7492
| 2024-05-16 | 4: 117.1399
| 2024-05-18 | 029: 95.7127
| 2024-05-19 | 033: 138.8532
TOTAL |  | 4: 213.1254; 029: 346.3144; 031: 399.8887; 033: 169.6024

## 2024-05-05
Pacific Restoration Group, Inc.
333333 Project Beta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | feet | ls | cubic yards | rolls | rolls | feet | feet | acres | ls
| 2024-04-29 | 4: 769.9633
| 2024-04-30 | 5: 237.7043
| 2024-05-02 | 030: 41.7024
| 2024-05-04 | 032: 229.8165
| 2024-05-05 | 4: 263.8486
TOTAL |  | 4: 1033.8119; 5: 237.7043; 030: 41.7024; 032: 229.8165

## 2024-04-28
Pacific Restoration Group, Inc.
333333 Project Beta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | feet | ls | cubic yards | rolls | rolls | feet | feet | acres | ls
| 2024-04-23 | 030: 85.5871; 031: 78.0226
| 2024-04-24 | 032: 263.6577
| 2024-04-25 | 5: 68.2607
| 2024-04-26 | 4: 154.0565; 030: 288.4394
| 2024-04-27 | 2: 0.5863
| 2024-04-28 | 029: 20.4829
TOTAL |  |  | 0.5863 | 154.0565 | 68.2607 | 20.4829 | 374.0264 | 78.0226 | 263.6577

## 2024-04-21
Pacific Restoration Group, Inc.
333333 Project Beta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | feet | ls | cubic yards | rolls | rolls | feet | feet | acres | ls
| 2024-04-17 | 4: 314.2014; 030: 233.411
| 2024-04-18 | 5: 100.6302
| 2024-04-19 | 2: 97.534
TOTAL |  | 2: 97.534; 4: 314.2014; 5: 100.6302; 030: 233.411

## 2024-04-14
Pacific Restoration Group, Inc.
333333 Project Beta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | feet | ls | cubic yards | rolls | rolls | feet | feet | acres | ls
| 2024-04-10 | 4: 22.9089; 030: 124.3877
| 2024-04-11 | 2: 361.0555; 030: 481.3232; 032: 166.2373
| 2024-04-12 | 5: 27.7229
| 2024-04-14 | 033: 5.4521
TOTAL |  |  | 361.0555 | 22.9089 | 27.7229 |  | 605.7109 |  | 166.2373 | 5.4521

## 2024-04-07
Pacific Restoration Group, Inc.
333333 Project Beta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | feet | ls | cubic yards | rolls | rolls | feet | feet | acres | ls
| 2024-04-04 | 033: 70.8551
| 2024-04-05 | 033: 4.9842
TOTAL |  | 033: 75.8393

## 2024-03-24
Pacific Restoration Group, Inc.
333333 Project Beta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | feet | ls | cubic yards | rolls | rolls | feet | feet | acres | ls
| 2024-03-19 | 5: 253.7428; 030: 158.3876
| 2024-03-22 | 033: 224.1807
TOTAL |  | 5: 253.7428; 030: 158.3876; 033: 224.1807

## 2024-03-17
Pacific Restoration Group, Inc.
333333 Project Beta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | feet | ls | cubic yards | rolls | rolls | feet | feet | acres | ls
| 2024-03-11 | 5: 82.0729; 029: 68.6112; 033: 112.6002
| 2024-03-14 | 030: 72.4331
| 2024-03-15 | 2: 606.3342; 032: 109.2246
| 2024-03-17 | 030: 275.0706
TOTAL |  |  | 606.3342 |  | 82.0729 | 68.6112 | 347.5037 |  | 109.2246 | 112.6002

## 2024-03-10
Pacific Restoration Group, Inc.
333333 Project Beta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | feet | ls | cubic yards | rolls | rolls | feet | feet | acres | ls
| 2024-03-04 | 033: 241.3152
| 2024-03-07 | 4: 197.9313; 5: 355.3442; 031: 403.3632
| 2024-03-08 | 2: 88.0168
| 2024-03-10 | 2: 16.2063; 4: 776.9505; 032: 372.7337
TOTAL |  |  | 104.2231 | 974.8818 | 355.3442 |  |  | 403.3632 | 372.7337 | 241.3152

## 2024-03-03
Pacific Restoration Group, Inc.
333333 Project Beta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | feet | ls | cubic yards | rolls | rolls | feet | feet | acres | ls
| 2024-02-29 | 032: 85.7367
| 2024-03-01 | 1: 68.8328
| 2024-03-02 | 5: 527.1391
TOTAL |  | 1: 68.8328; 5: 527.1391; 032: 85.7367

## 2024-02-25
Pacific Restoration Group, Inc.
333333 Project Beta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | feet | ls | cubic yards | rolls | rolls | feet | feet | acres | ls
| 2024-02-21 | 5: 85.5852
| 2024-02-22 | 033: 56.535
| 2024-02-25 | 5: 442.7157
TOTAL |  | 5: 528.301; 033: 56.535

## 2024-02-18
Pacific Restoration Group, Inc.
333333 Project Beta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | feet | ls | cubic yards | rolls | rolls | feet | feet | acres | ls
| 2024-02-12 | 4: 44.8526
| 2024-02-13 | 029: 437.4888
| 2024-02-16 | 031: 481.5058
| 2024-02-17 | 1: 133.397; 029: 253.1793; 031: 193.7161
| 2024-02-18 | 033: 163.7535
TOTAL |  | 1: 133.397; 4: 44.8526; 029: 690.6681; 031: 675.2219; 033: 163.7535

## 2024-02-11
Pacific Restoration Group, Inc.
333333 Project Beta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | feet | ls | cubic yards | rolls | rolls | feet | feet | acres | ls
| 2024-02-05 | 033: 371.2042
| 2024-02-06 | 5: 848.8047
| 2024-02-08 | 2: 294.1498
| 2024-02-10 | 2: 510.0626; 030: 29.2814
| 2024-02-11 | 1: 38.1001
TOTAL |  | 1: 38.1001; 2: 804.2124; 5: 848.8047; 030: 29.2814; 033: 371.2042

## 2024-02-04
Pacific Restoration Group, Inc.
333333 Project Beta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | feet | ls | cubic yards | rolls | rolls | feet | feet | acres | ls
| 2024-01-30 | 032: 641.5347
| 2024-01-31 | 4: 49.3992
| 2024-02-04 | 031: 363.5147
TOTAL |  | 4: 49.3992; 031: 363.5147; 032: 641.5347

## 2024-01-28
Pacific Restoration Group, Inc.
333333 Project Beta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | feet | ls | cubic yards | rolls | rolls | feet | feet | acres | ls
| 2024-01-25 | 029: 263.7967; 031: 733.7851
| 2024-01-26 | 030: 193.216
TOTAL |  | 029: 263.7967; 030: 193.216; 031: 733.7851

## 2024-01-21
Pacific Restoration Group, Inc.
333333 Project Beta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | feet | ls | cubic yards | rolls | rolls | feet | feet | acres | ls
| 2024-01-16 | 5: 340.9779; 030: 87.6233
| 2024-01-17 | 029: 530.6868
| 2024-01-18 | 032: 502.31
| 2024-01-19 | 4: 338.2687
TOTAL |  | 4: 338.2687; 5: 340.9779; 029: 530.6868; 030: 87.6233; 032: 502.31

## 2024-01-14
Pacific Restoration Group, Inc.
333333 Project Beta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | feet | ls | cubic yards | rolls | rolls | feet | feet | acres | ls
| 2024-01-11 | 033: 68.1223
| 2024-01-13 | 1: 104.1021
| 2024-01-14 | 033: 378.4183
TOTAL |  | 1: 104.1021; 033: 446.5406

## 2024-01-07
Pacific Restoration Group, Inc.
333333 Project Beta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | feet | ls | cubic yards | rolls | rolls | feet | feet | acres | ls
| 2024-01-01 | 2: 36.3015
| 2024-01-02 | 030: 574.3274
TOTAL |  | 2: 36.3015; 030: 574.3274