## 05-27-24
Pacific Restoration Group, Inc.
333333 Project Gamma
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | feet | bags | square feet | acres | acres | pounds | bags | ls | square feet
| 2024-05-22 | 030: 122.2252
| 2024-05-27 | 4: 53.0723; 5: 420.7591
TOTAL |  | 4: 53.0723; 5: 420.7591; 030: 122.2252

## 05-20-24
Pacific Restoration Group, Inc.
333333 Project Gamma
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | feet | bags | square feet | acres | acres | pounds | bags | ls | square feet
| 2024-05-14 | 033: 519.9471
| 2024-05-17 | 031: 165.5493
| 2024-05-18 | 5: 51.1339
| 2024-05-19 | 032: 47.408
TOTAL |  | 5: 51.1339; 031: 165.5493; 032: 47.408; 033: 519.9471

## 05-13-24
Pacific Restoration Group, Inc.
333333 Project Gamma
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | feet | bags | square feet | acres | acres | pounds | bags | ls | square feet
| 2024-05-07 | 4: 19.3677; 033: 189.1482
| 2024-05-09 | 1: 680.4963; 2: 216.3281; 4: 272.2529; 5: 667.9605; 032: 140.9953
| 2024-05-10 | 029: 55.7672; 032: 201.9926
| 2024-05-11 | 032: 84.6883
TOTAL |  | 680.4963 | 216.3281 | 291.6206 | 667.9605 | 55.7672 |  |  | 427.6762 | 189.1482

## 05-06-24
Pacific Restoration Group, Inc.
333333 Project Gamma
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | feet | bags | square feet | acres | acres | pounds | bags | ls | square feet
| 2024-05-05 | 1: 149.5538
TOTAL |  | 1: 149.5538

## 04-29-24
Pacific Restoration Group, Inc.
333333 Project Gamma
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | feet | bags | square feet | acres | acres | pounds | bags | ls | square feet
| 2024-04-24 | 5: 0.63989; 030: 266.6637
| 2024-04-28 | 4: 830.9839; 032: 607.4342
TOTAL |  | 4: 830.9839; 5: 0.63989; 030: 266.6637; 032: 607.4342

## 04-22-24
Pacific Restoration Group, Inc.
333333 Project Gamma
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | feet | bags | square feet | acres | acres | pounds | bags | ls | square feet
| 2024-04-16 | 029: 308.5158
| 2024-04-21 | 029: 30.7414
TOTAL |  | 029: 339.2571

## 04-15-24
Pacific Restoration Group, Inc.
333333 Project Gamma
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | feet | bags | square feet | acres | acres | pounds | bags | ls | square feet
| 2024-04-11 | 2: 450.6183; 033: 618.4905
| 2024-04-13 | 029: 387.2736
TOTAL |  | 2: 450.6183; 029: 387.2736; 033: 618.4905

## 04-08-24
Pacific Restoration Group, Inc.
333333 Project Gamma
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | feet | bags | square feet | acres | acres | pounds | bags | ls | square feet
| 2024-04-06 | 032: 321.1035
TOTAL |  | 032: 321.1035

## 04-01-24
Pacific Restoration Group, Inc.
333333 Project Gamma
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | feet | bags | square feet | acres | acres | pounds | bags | ls | square feet
| 2024-03-28 | 032: 699.2426
| 2024-03-29 | 2: 553.2136; 029: 414.1525
| 2024-03-30 | 029: 388.9039
| 2024-03-31 | 1: 654.5036
| 2024-04-01 | 032: 330.0744
TOTAL |  | 1: 654.5036; 2: 553.2136; 029: 803.0564; 032: 1029.317

## 03-25-24
Pacific Restoration Group, Inc.
333333 Project Gamma
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | feet | bags | square feet | acres | acres | pounds | bags | ls | square feet
| 2024-03-19 | 5: 1.3447
| 2024-03-20 | 2: 261.8713
| 2024-03-21 | 033: 599.5261
| 2024-03-22 | 030: 358.5996
| 2024-03-23 | 029: 334.3646
| 2024-03-25 | 1: 72.6091; 5: 100.8861; 030: 349.3873; 032: 120.9607
TOTAL |  | 72.6091 | 261.8713 |  | 102.2308 | 334.3646 | 707.9869 |  | 120.9607 | 599.5261

## 03-18-24
Pacific Restoration Group, Inc.
333333 Project Gamma
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | feet | bags | square feet | acres | acres | pounds | bags | ls | square feet
| 2024-03-14 | 030: 223.991
| 2024-03-16 | 5: 164.8171
| 2024-03-17 | 029: 16.751
TOTAL |  | 5: 164.8171; 029: 16.751; 030: 223.991

## 03-11-24
Pacific Restoration Group, Inc.
333333 Project Gamma
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | feet | bags | square feet | acres | acres | pounds | bags | ls | square feet
| 2024-03-06 | 033: 24.6735
| 2024-03-07 | 033: 165.7952
| 2024-03-08 | 031: 509.3671
| 2024-03-10 | 1: 233.6126
TOTAL |  | 1: 233.6126; 031: 509.3671; 033: 190.4687

## 03-04-24
Pacific Restoration Group, Inc.
333333 Project Gamma
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | feet | bags | square feet | acres | acres | pounds | bags | ls | square feet
| 2024-02-28 | 029: 156.7361
| 2024-02-29 | 2: 17.2797
| 2024-03-02 | 029: 155.5709
| 2024-03-04 | 1: 97.8016
TOTAL |  | 1: 97.8016; 2: 17.2797; 029: 312.307

## 02-26-24
Pacific Restoration Group, Inc.
333333 Project Gamma
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | feet | bags | square feet | acres | acres | pounds | bags | ls | square feet
| 2024-02-23 | 032: 107.9851
| 2024-02-24 | 029: 123.0976
| 2024-02-25 | 029: 384.7715; 032: 18.1549
TOTAL |  | 029: 507.8691; 032: 126.1401

## 02-19-24
Pacific Restoration Group, Inc.
333333 Project Gamma
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | feet | bags | square feet | acres | acres | pounds | bags | ls | square feet
| 2024-02-14 | 5: 661.1211; 030: 830.496; 031: 252.348
| 2024-02-18 | 5: 4.8448; 029: 35.4757
TOTAL |  | 5: 665.9658; 029: 35.4757; 030: 830.496; 031: 252.348

## 02-12-24
Pacific Restoration Group, Inc.
333333 Project Gamma
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | feet | bags | square feet | acres | acres | pounds | bags | ls | square feet
| 2024-02-06 | 4: 504.006; 031: 519.0232
| 2024-02-08 | 031: 595.3393
TOTAL |  | 4: 504.006; 031: 1114.3625

## 02-05-24
Pacific Restoration Group, Inc.
333333 Project Gamma
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | feet | bags | square feet | acres | acres | pounds | bags | ls | square feet
| 2024-01-30 | 1: 100.084
| 2024-02-02 | 4: 195.971; 029: 21.1236
| 2024-02-03 | 5: 44.3791
| 2024-02-04 | 1: 95.4963; 2: 118.9686; 031: 404.3171; 033: 675.7757
TOTAL |  | 195.5802 | 118.9686 | 195.971 | 44.3791 | 21.1236 |  | 404.3171 |  | 675.7757

## 01-29-24
Pacific Restoration Group, Inc.
333333 Project Gamma
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | feet | bags | square feet | acres | acres | pounds | bags | ls | square feet
| 2024-01-23 | 030: 316.1814; 031: 272.3795
| 2024-01-24 | 1: 6.6934
| 2024-01-25 | 030: 341.4009
| 2024-01-27 | 033: 96.3646
| 2024-01-28 | 029: 330.583
| 2024-01-29 | 4: 32.2696; 032: 41.6724
TOTAL |  | 6.6934 |  | 32.2696 |  | 330.583 | 657.5823 | 272.3795 | 41.6724 | 96.3646

## 01-22-24
Pacific Restoration Group, Inc.
333333 Project Gamma
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | feet | bags | square feet | acres | acres | pounds | bags | ls | square feet
| 2024-01-18 | 029: 473.3815
| 2024-01-19 | 032: 320.1018
| 2024-01-21 | 5: 143.5145
| 2024-01-22 | 2: 293.9391
TOTAL |  | 2: 293.9391; 5: 143.5145; 029: 473.3815; 032: 320.1018

## 01-15-24
Pacific Restoration Group, Inc.
333333 Project Gamma
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | feet | bags | square feet | acres | acres | pounds | bags | ls | square feet
| 2024-01-14 | 5: 159.6077
| 2024-01-15 | 032: 306.4674
TOTAL |  | 5: 159.6077; 032: 306.4674

## 01-08-24
Pacific Restoration Group, Inc.
333333 Project Gamma
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | feet | bags | square feet | acres | acres | pounds | bags | ls | square feet
| 2024-01-02 | 032: 369.0953; 033: 254.8692
| 2024-01-03 | 033: 374.777
| 2024-01-05 | 1: 130.764; 5: 723.6711
| 2024-01-06 | 029: 379.5105
| 2024-01-08 | 033: 59.4043
TOTAL |  | 1: 130.764; 5: 723.6711; 029: 379.5105; 032: 369.0953; 033: 689.0505