## 2024-05-30
Pacific Restoration Group, Inc.
444444 Project Delta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | tons | ls | square meters | rolls | acres | square feet | bags | feet | tons
| 2024-05-27 | 5: 731.6245; 033: 256.9494
| 2024-05-29 | 030: 182.3213
| 2024-05-30 | 5: 101.5528
TOTAL |  | 5: 833.1773; 030: 182.3213; 033: 256.9494

## 2024-05-26
Pacific Restoration Group, Inc.
444444 Project Delta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | tons | ls | square meters | rolls | acres | square feet | bags | feet | tons
| 2024-05-20 | 031: 256.0232
| 2024-05-22 | 2: 372.8706; 031: 73.4075
| 2024-05-24 | 030: 19.6377
TOTAL |  | 2: 372.8706; 030: 19.6377; 031: 329.4307

## 2024-05-19
Pacific Restoration Group, Inc.
444444 Project Delta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | tons | ls | square meters | rolls | acres | square feet | bags | feet | tons
| 2024-05-13 | 032: 310.2499
| 2024-05-17 | 032: 619.7213; 033: 4.2222
| 2024-05-19 | 029: 4.7422
TOTAL |  | 029: 4.7422; 032: 929.9713; 033: 4.2222

## 2024-05-12
Pacific Restoration Group, Inc.
444444 Project Delta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | tons | ls | square meters | rolls | acres | square feet | bags | feet | tons
| 2024-05-07 | 030: 384.4846
| 2024-05-08 | 4: 295.2078
TOTAL |  | 4: 295.2078; 030: 384.4846

## 2024-05-05
Pacific Restoration Group, Inc.
444444 Project Delta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | tons | ls | square meters | rolls | acres | square feet | bags | feet | tons
| 2024-04-30 | 2: 276.325; 030: 442.5156
| 2024-05-04 | 5: 407.9794
TOTAL |  | 2: 276.325; 5: 407.9794; 030: 442.5156

## 2024-04-28
Pacific Restoration Group, Inc.
444444 Project Delta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | tons | ls | square meters | rolls | acres | square feet | bags | feet | tons
| 2024-04-22 | 033: 134.7999
| 2024-04-23 | 2: 703.3508
| 2024-04-24 | 029: 319.3002
| 2024-04-25 | 1: 261.3325
| 2024-04-26 | 031: 58.2236
TOTAL |  | 1: 261.3325; 2: 703.3508; 029: 319.3002; 031: 58.2236; 033: 134.7999

## 2024-04-21
Pacific Restoration Group, Inc.
444444 Project Delta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | tons | ls | square meters | rolls | acres | square feet | bags | feet | tons
| 2024-04-15 | 4: 631.2017
| 2024-04-17 | 1: 1209.5513; 029: 182.5081
| 2024-04-18 | 029: 107.7349
| 2024-04-20 | 031: 43.1123
TOTAL |  | 1: 1209.5513; 4: 631.2017; 029: 290.243; 031: 43.1123

## 2024-04-14
Pacific Restoration Group, Inc.
444444 Project Delta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | tons | ls | square meters | rolls | acres | square feet | bags | feet | tons
| 2024-04-12 | 4: 499.6723
| 2024-04-13 | 4: 211.8358
| 2024-04-14 | 4: 270.4679
TOTAL |  | 4: 981.9759

## 2024-04-07
Pacific Restoration Group, Inc.
444444 Project Delta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | tons | ls | square meters | rolls | acres | square feet | bags | feet | tons
| 2024-04-01 | 1: 131.5614; 5: 357.0184; 032: 226.1447
| 2024-04-05 | 032: 49.8317
| 2024-04-07 | 029: 75.827
TOTAL |  | 1: 131.5614; 5: 357.0184; 029: 75.827; 032: 275.9764

## 2024-03-31
Pacific Restoration Group, Inc.
444444 Project Delta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | tons | ls | square meters | rolls | acres | square feet | bags | feet | tons
| 2024-03-27 | 5: 824.6745
| 2024-03-28 | 033: 363.7846
| 2024-03-30 | 031: 477.3826
| 2024-03-31 | 029: 625.1592
TOTAL |  | 5: 824.6745; 029: 625.1592; 031: 477.3826; 033: 363.7846

## 2024-03-24
Pacific Restoration Group, Inc.
444444 Project Delta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | tons | ls | square meters | rolls | acres | square feet | bags | feet | tons
| 2024-03-18 | 030: 71.1581
| 2024-03-21 | 2: 123.0479; 032: 64.5003
| 2024-03-23 | 029: 157.4651; 032: 81.3167
TOTAL |  | 2: 123.0479; 029: 157.4651; 030: 71.1581; 032: 145.817

## 2024-03-17
Pacific Restoration Group, Inc.
444444 Project Delta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | tons | ls | square meters | rolls | acres | square feet | bags | feet | tons
| 2024-03-11 | 032: 341.7722
| 2024-03-14 | 4: 38.9903; 033: 135.8877
| 2024-03-15 | 029: 198.8176
| 2024-03-17 | 029: 807.6053
TOTAL |  | 4: 38.9903; 029: 1006.4229; 032: 341.7722; 033: 135.8877

## 2024-03-10
Pacific Restoration Group, Inc.
444444 Project Delta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | tons | ls | square meters | rolls | acres | square feet | bags | feet | tons
| 2024-03-04 | 4: 124.004
| 2024-03-05 | 032: 645.6133
| 2024-03-08 | 030: 63.6831
| 2024-03-09 | 1: 368.6466; 4: 651.872
| 2024-03-10 | 029: 0.54573; 030: 235.2137
TOTAL |  | 1: 368.6466; 4: 775.8759; 029: 0.54573; 030: 298.8968; 032: 645.6133

## 2024-03-03
Pacific Restoration Group, Inc.
444444 Project Delta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | tons | ls | square meters | rolls | acres | square feet | bags | feet | tons
| 2024-02-26 | 4: 68.1758
| 2024-02-28 | 1: 9.0483
| 2024-02-29 | 4: 194.3277; 031: 2.8998
| 2024-03-01 | 031: 373.268
| 2024-03-02 | 4: 115.4167
TOTAL |  | 1: 9.0483; 4: 377.9203; 031: 376.1678

## 2024-02-25
Pacific Restoration Group, Inc.
444444 Project Delta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | tons | ls | square meters | rolls | acres | square feet | bags | feet | tons
| 2024-02-19 | 2: 299.6916; 032: 40.8718
| 2024-02-21 | 4: 87.9183; 029: 551.1977
| 2024-02-23 | 1: 214.2515; 4: 496.7641
| 2024-02-24 | 4: 405.893
TOTAL |  | 1: 214.2515; 2: 299.6916; 4: 990.5754; 029: 551.1977; 032: 40.8718

## 2024-02-18
Pacific Restoration Group, Inc.
444444 Project Delta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | tons | ls | square meters | rolls | acres | square feet | bags | feet | tons
| 2024-02-13 | 029: 226.8809
| 2024-02-14 | 032: 263.7855
| 2024-02-16 | 4: 234.2854
TOTAL |  | 4: 234.2854; 029: 226.8809; 032: 263.7855

## 2024-02-11
Pacific Restoration Group, Inc.
444444 Project Delta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | tons | ls | square meters | rolls | acres | square feet | bags | feet | tons
| 2024-02-05 | 031: 109.3492
| 2024-02-08 | 030: 40.1763; 031: 13.9287
| 2024-02-10 | 029: 28.2579
TOTAL |  | 029: 28.2579; 030: 40.1763; 031: 123.2779

## 2024-02-04
Pacific Restoration Group, Inc.
444444 Project Delta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | tons | ls | square meters | rolls | acres | square feet | bags | feet | tons
| 2024-01-30 | 1: 62.0037
| 2024-02-01 | 029: 146.9578
| 2024-02-02 | 5: 125.0127
| 2024-02-04 | 1: 123.3669
TOTAL |  | 1: 185.3706; 5: 125.0127; 029: 146.9578

## 2024-01-28
Pacific Restoration Group, Inc.
444444 Project Delta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | tons | ls | square meters | rolls | acres | square feet | bags | feet | tons
| 2024-01-22 | 1: 97.1907
| 2024-01-24 | 031: 643.294
| 2024-01-26 | 033: 24.2797
| 2024-01-28 | 2: 286.0318
TOTAL |  | 1: 97.1907; 2: 286.0318; 031: 643.294; 033: 24.2797

## 2024-01-21
Pacific Restoration Group, Inc.
444444 Project Delta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | tons | ls | square meters | rolls | acres | square feet | bags | feet | tons
| 2024-01-17 | 030: 211.1415
| 2024-01-18 | 032: 663.6895
| 2024-01-20 | 031: 73.3098; 033: 24.5663
| 2024-01-21 | 1: 61.4699; 033: 57.8942
TOTAL |  | 1: 61.4699; 030: 211.1415; 031: 73.3098; 032: 663.6895; 033: 82.4605

## 2024-01-14
Pacific Restoration Group, Inc.
444444 Project Delta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | tons | ls | square meters | rolls | acres | square feet | bags | feet | tons
| 2024-01-08 | 5: 214.4086
| 2024-01-09 | 031: 196.4489
| 2024-01-11 | 029: 437.8397; 033: 38.5383
| 2024-01-14 | 1: 633.8999
TOTAL |  | 1: 633.8999; 5: 214.4086; 029: 437.8397; 031: 196.4489; 033: 38.5383

## 2024-01-07
Pacific Restoration Group, Inc.
444444 Project Delta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | tons | ls | square meters | rolls | acres | square feet | bags | feet | tons
| 2024-01-01 | 2: 198.4607; 5: 217.794
| 2024-01-02 | 031: 156.892
| 2024-01-03 | 1: 292.6041
TOTAL |  | 1: 292.6041; 2: 198.4607; 5: 217.794; 031: 156.892