## 05-29-24
Pacific Restoration Group, Inc.
444444 Project Epsilon
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | acres | meters | bags | tons | cubic yards | cubic yards | square feet | gallons | feet
| 2024-05-29 | 030: 107.2594; 031: 32.5745
TOTAL |  | 030: 107.2594; 031: 32.5745

## 05-28-24
Pacific Restoration Group, Inc.
444444 Project Epsilon
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | acres | meters | bags | tons | cubic yards | cubic yards | square feet | gallons | feet
| 2024-05-22 | 031: 42.1877
| 2024-05-23 | 1: 418.951; 032: 347.9031
| 2024-05-25 | 4: 433.6662
| 2024-05-27 | 031: 140.6148
TOTAL |  | 1: 418.951; 4: 433.6662; 031: 182.8025; 032: 347.9031

## 05-21-24
Pacific Restoration Group, Inc.
444444 Project Epsilon
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | acres | meters | bags | tons | cubic yards | cubic yards | square feet | gallons | feet
| 2024-05-15 | 030: 45.8454
| 2024-05-16 | 2: 111.1749
| 2024-05-17 | 4: 168.9784
| 2024-05-18 | 5: 77.7877
| 2024-05-19 | 2: 473.0415; 4: 85.2907
| 2024-05-21 | 031: 192.1916; 032: 51.1811
TOTAL |  |  | 584.2164 | 254.2691 | 77.7877 |  | 45.8454 | 192.1916 | 51.1811

## 05-14-24
Pacific Restoration Group, Inc.
444444 Project Epsilon
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | acres | meters | bags | tons | cubic yards | cubic yards | square feet | gallons | feet
| 2024-05-08 | 2: 411.8814; 033: 232.8633
| 2024-05-10 | 5: 483.3085
| 2024-05-11 | 1: 28.5838; 032: 420.1723
| 2024-05-14 | 029: 248.7765; 031: 166.9658
TOTAL |  | 28.5838 | 411.8814 |  | 483.3085 | 248.7765 |  | 166.9658 | 420.1723 | 232.8633

## 05-07-24
Pacific Restoration Group, Inc.
444444 Project Epsilon
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | acres | meters | bags | tons | cubic yards | cubic yards | square feet | gallons | feet
| 2024-05-01 | 030: 253.7757
| 2024-05-03 | 033: 67.195
| 2024-05-06 | 2: 797.1887
| 2024-05-07 | 032: 184.6555
TOTAL |  | 2: 797.1887; 030: 253.7757; 032: 184.6555; 033: 67.195

## 04-30-24
Pacific Restoration Group, Inc.
444444 Project Epsilon
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | acres | meters | bags | tons | cubic yards | cubic yards | square feet | gallons | feet
| 2024-04-27 | 4: 224.4974; 031: 211.3943
| 2024-04-29 | 033: 181.9284
TOTAL |  | 4: 224.4974; 031: 211.3943; 033: 181.9284

## 04-23-24
Pacific Restoration Group, Inc.
444444 Project Epsilon
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | acres | meters | bags | tons | cubic yards | cubic yards | square feet | gallons | feet
| 2024-04-19 | 2: 221.3355
| 2024-04-20 | 029: 355.9757
| 2024-04-23 | 1: 586.5682
TOTAL |  | 1: 586.5682; 2: 221.3355; 029: 355.9757

## 04-16-24
Pacific Restoration Group, Inc.
444444 Project Epsilon
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | acres | meters | bags | tons | cubic yards | cubic yards | square feet | gallons | feet
| 2024-04-10 | 029: 88.4967; 030: 67.2633
| 2024-04-13 | 1: 11.5166
| 2024-04-15 | 5: 144.1428; 030: 176.3891
TOTAL |  | 1: 11.5166; 5: 144.1428; 029: 88.4967; 030: 243.6523

## 04-09-24
Pacific Restoration Group, Inc.
444444 Project Epsilon
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | acres | meters | bags | tons | cubic yards | cubic yards | square feet | gallons | feet
| 2024-04-03 | 031: 110.4231
| 2024-04-04 | 4: 238.2518; 032: 616.0624
| 2024-04-08 | 4: 512.5616; 031: 16.9841
| 2024-04-09 | 029: 147.775
TOTAL |  | 4: 750.8135; 029: 147.775; 031: 127.4072; 032: 616.0624

## 04-02-24
Pacific Restoration Group, Inc.
444444 Project Epsilon
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | acres | meters | bags | tons | cubic yards | cubic yards | square feet | gallons | feet
| 2024-03-30 | 033: 119.0321
| 2024-03-31 | 1: 210.3267; 030: 703.507
| 2024-04-02 | 033: 47.1541
TOTAL |  | 1: 210.3267; 030: 703.507; 033: 166.1861

## 03-26-24
Pacific Restoration Group, Inc.
444444 Project Epsilon
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | acres | meters | bags | tons | cubic yards | cubic yards | square feet | gallons | feet
| 2024-03-20 | 032: 36.0419
| 2024-03-23 | 2: 692.5612
| 2024-03-24 | 029: 505.4612
| 2024-03-26 | 032: 133.1752
TOTAL |  | 2: 692.5612; 029: 505.4612; 032: 169.2171

## 03-19-24
Pacific Restoration Group, Inc.
444444 Project Epsilon
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | acres | meters | bags | tons | cubic yards | cubic yards | square feet | gallons | feet
| 2024-03-17 | 033: 62.8376
TOTAL |  | 033: 62.8376

## 03-12-24
Pacific Restoration Group, Inc.
444444 Project Epsilon
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | acres | meters | bags | tons | cubic yards | cubic yards | square feet | gallons | feet
| 2024-03-07 | 1: 764.1172
| 2024-03-09 | 1: 97.7686; 5: 92.0233
TOTAL |  | 1: 861.8858; 5: 92.0233

## 03-05-24
Pacific Restoration Group, Inc.
444444 Project Epsilon
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | acres | meters | bags | tons | cubic yards | cubic yards | square feet | gallons | feet
| 2024-02-28 | 1: 418.0067; 4: 560.4122
| 2024-03-01 | 1: 177.4185; 029: 25.3073
| 2024-03-02 | 4: 148.1908
| 2024-03-03 | 1: 3.9394
TOTAL |  | 1: 599.3645; 4: 708.603; 029: 25.3073

## 02-27-24
Pacific Restoration Group, Inc.
444444 Project Epsilon
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | acres | meters | bags | tons | cubic yards | cubic yards | square feet | gallons | feet
| 2024-02-21 | 031: 25.0853
| 2024-02-23 | 032: 92.239
| 2024-02-24 | 033: 706.5491
| 2024-02-26 | 5: 229.3715; 031: 60.6885
| 2024-02-27 | 5: 825.3129
TOTAL |  | 5: 1054.6844; 031: 85.7738; 032: 92.239; 033: 706.5491

## 02-20-24
Pacific Restoration Group, Inc.
444444 Project Epsilon
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | acres | meters | bags | tons | cubic yards | cubic yards | square feet | gallons | feet
| 2024-02-15 | 2: 572.9579; 4: 126.0724
| 2024-02-16 | 030: 7.0436; 032: 357.1848
| 2024-02-17 | 5: 5.685; 029: 676.4882
| 2024-02-18 | 2: 677.1113
TOTAL |  |  | 1250.0691 | 126.0724 | 5.685 | 676.4882 | 7.0436 |  | 357.1848

## 02-13-24
Pacific Restoration Group, Inc.
444444 Project Epsilon
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | acres | meters | bags | tons | cubic yards | cubic yards | square feet | gallons | feet
| 2024-02-08 | 032: 185.5815; 033: 176.3386
| 2024-02-09 | 030: 353.3533
| 2024-02-10 | 2: 17.1414
| 2024-02-13 | 5: 30.8124
TOTAL |  | 2: 17.1414; 5: 30.8124; 030: 353.3533; 032: 185.5815; 033: 176.3386

## 02-06-24
Pacific Restoration Group, Inc.
444444 Project Epsilon
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | acres | meters | bags | tons | cubic yards | cubic yards | square feet | gallons | feet
| 2024-01-31 | 031: 93.0011
| 2024-02-04 | 029: 60.111
TOTAL |  | 029: 60.111; 031: 93.0011

## 01-30-24
Pacific Restoration Group, Inc.
444444 Project Epsilon
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | acres | meters | bags | tons | cubic yards | cubic yards | square feet | gallons | feet
| 2024-01-25 | 030: 60.1177
| 2024-01-27 | 032: 10.2328
| 2024-01-30 | 032: 244.3842
TOTAL |  | 030: 60.1177; 032: 254.617

## 01-23-24
Pacific Restoration Group, Inc.
444444 Project Epsilon
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | acres | meters | bags | tons | cubic yards | cubic yards | square feet | gallons | feet
| 2024-01-17 | 1: 53.7136
| 2024-01-21 | 032: 362.2391
TOTAL |  | 1: 53.7136; 032: 362.2391

## 01-16-24
Pacific Restoration Group, Inc.
444444 Project Epsilon
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | acres | meters | bags | tons | cubic yards | cubic yards | square feet | gallons | feet
| 2024-01-10 | 2: 236.6079; 030: 77.9596
| 2024-01-11 | 4: 181.2909
| 2024-01-15 | 031: 0.90634
| 2024-01-16 | 4: 30.0809
TOTAL |  | 2: 236.6079; 4: 211.3718; 030: 77.9596; 031: 0.90634

## 01-09-24
Pacific Restoration Group, Inc.
444444 Project Epsilon
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | acres | meters | bags | tons | cubic yards | cubic yards | square feet | gallons | feet
| 2024-01-03 | 030: 30.0072
| 2024-01-04 | 031: 202.6171
| 2024-01-05 | 031: 618.4126
| 2024-01-06 | 5: 620.6252; 031: 357.293; 033: 238.5615
| 2024-01-09 | 5: 118.3318
TOTAL |  | 5: 738.957; 030: 30.0072; 031: 1178.3227; 033: 238.5615