## 05-29-24
Pacific Restoration Group, Inc.
555555 Project Beta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | cubic yards | square feet | square meters | cubic yards | meters | ls | ls | bags | pounds
| 2024-05-29 | 030: 251.3122
TOTAL |  | 030: 251.3122

## 05-28-24
Pacific Restoration Group, Inc.
555555 Project Beta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | cubic yards | square feet | square meters | cubic yards | meters | ls | ls | bags | pounds
| 2024-05-22 | 1: 907.7582
| 2024-05-23 | 1: 91.286
| 2024-05-24 | 2: 577.3646
TOTAL |  | 1: 999.0442; 2: 577.3646

## 05-21-24
Pacific Restoration Group, Inc.
555555 Project Beta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | cubic yards | square feet | square meters | cubic yards | meters | ls | ls | bags | pounds
| 2024-05-19 | 032: 149.6647
| 2024-05-21 | 030: 101.9003
TOTAL |  | 030: 101.9003; 032: 149.6647

## 05-14-24
Pacific Restoration Group, Inc.
555555 Project Beta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | cubic yards | square feet | square meters | cubic yards | meters | ls | ls | bags | pounds
| 2024-05-12 | 2: 18.2849
TOTAL |  | 2: 18.2849

## 05-07-24
Pacific Restoration Group, Inc.
555555 Project Beta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | cubic yards | square feet | square meters | cubic yards | meters | ls | ls | bags | pounds
| 2024-05-03 | 4: 33.617; 030: 131.2141
| 2024-05-05 | 033: 753.609
TOTAL |  | 4: 33.617; 030: 131.2141; 033: 753.609

## 04-30-24
Pacific Restoration Group, Inc.
555555 Project Beta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | cubic yards | square feet | square meters | cubic yards | meters | ls | ls | bags | pounds
| 2024-04-24 | 032: 128.3194; 033: 751.3823
| 2024-04-26 | 1: 45.7965
| 2024-04-27 | 5: 481.6622
| 2024-04-29 | 032: 116.4558
| 2024-04-30 | 029: 518.8439; 031: 74.0392
TOTAL |  | 45.7965 |  |  | 481.6622 | 518.8439 |  | 74.0392 | 244.7752 | 751.3823

## 04-23-24
Pacific Restoration Group, Inc.
555555 Project Beta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | cubic yards | square feet | square meters | cubic yards | meters | ls | ls | bags | pounds
| 2024-04-18 | 4: 132.7359
| 2024-04-19 | 029: 72.7878
| 2024-04-20 | 5: 655.0313
| 2024-04-21 | 031: 298.9283
TOTAL |  | 4: 132.7359; 5: 655.0313; 029: 72.7878; 031: 298.9283

## 04-16-24
Pacific Restoration Group, Inc.
555555 Project Beta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | cubic yards | square feet | square meters | cubic yards | meters | ls | ls | bags | pounds
| 2024-04-12 | 5: 708.7551
| 2024-04-13 | 029: 549.3131
| 2024-04-14 | 4: 905.0579
| 2024-04-15 | 030: 553.6662
TOTAL |  | 4: 905.0579; 5: 708.7551; 029: 549.3131; 030: 553.6662

## 04-09-24
Pacific Restoration Group, Inc.
555555 Project Beta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | cubic yards | square feet | square meters | cubic yards | meters | ls | ls | bags | pounds
| 2024-04-03 | 029: 12.0569
| 2024-04-04 | 031: 390.0669
| 2024-04-05 | 033: 189.056
| 2024-04-08 | 4: 172.5857; 5: 291.75; 033: 576.5109
| 2024-04-09 | 029: 667.1911
TOTAL |  | 4: 172.5857; 5: 291.75; 029: 679.2481; 031: 390.0669; 033: 765.5669

## 04-02-24
Pacific Restoration Group, Inc.
555555 Project Beta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | cubic yards | square feet | square meters | cubic yards | meters | ls | ls | bags | pounds
| 2024-03-28 | 2: 24.3276
| 2024-04-01 | 1: 739.3523; 2: 190.9081
TOTAL |  | 1: 739.3523; 2: 215.2357

## 03-26-24
Pacific Restoration Group, Inc.
555555 Project Beta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | cubic yards | square feet | square meters | cubic yards | meters | ls | ls | bags | pounds
| 2024-03-25 | 029: 117.5252; 030: 150.0444
| 2024-03-26 | 029: 242.294
TOTAL |  | 029: 359.8192; 030: 150.0444

## 03-19-24
Pacific Restoration Group, Inc.
555555 Project Beta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | cubic yards | square feet | square meters | cubic yards | meters | ls | ls | bags | pounds
| 2024-03-13 | 2: 48.3138
| 2024-03-18 | 4: 384.2849
| 2024-03-19 | 2: 203.264; 4: 385.1652; 032: 30.8103
TOTAL |  | 2: 251.5778; 4: 769.4501; 032: 30.8103

## 03-12-24
Pacific Restoration Group, Inc.
555555 Project Beta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | cubic yards | square feet | square meters | cubic yards | meters | ls | ls | bags | pounds
| 2024-03-08 | 2: 206.376
| 2024-03-09 | 5: 409.491
| 2024-03-10 | 2: 154.9213; 032: 259.567
| 2024-03-11 | 2: 453.2084; 5: 484.4762
| 2024-03-12 | 2: 401.9084; 4: 104.0677; 5: 233.1391
TOTAL |  | 2: 1216.4141; 4: 104.0677; 5: 1127.1062; 032: 259.567

## 03-05-24
Pacific Restoration Group, Inc.
555555 Project Beta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | cubic yards | square feet | square meters | cubic yards | meters | ls | ls | bags | pounds
| 2024-02-28 | 1: 320.0569
| 2024-03-01 | 4: 457.4174
| 2024-03-04 | 033: 535.4006
| 2024-03-05 | 2: 94.4934
TOTAL |  | 1: 320.0569; 2: 94.4934; 4: 457.4174; 033: 535.4006

## 02-27-24
Pacific Restoration Group, Inc.
555555 Project Beta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | cubic yards | square feet | square meters | cubic yards | meters | ls | ls | bags | pounds
| 2024-02-22 | 032: 158.9741
| 2024-02-23 | 031: 164.7533
| 2024-02-26 | 029: 74.0081
TOTAL |  | 029: 74.0081; 031: 164.7533; 032: 158.9741

## 02-20-24
Pacific Restoration Group, Inc.
555555 Project Beta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | cubic yards | square feet | square meters | cubic yards | meters | ls | ls | bags | pounds
| 2024-02-14 | 031: 30.8565
| 2024-02-16 | 1: 397.0449
| 2024-02-18 | 032: 646.3244
| 2024-02-20 | 033: 623.112
TOTAL |  | 1: 397.0449; 031: 30.8565; 032: 646.3244; 033: 623.112

## 02-13-24
Pacific Restoration Group, Inc.
555555 Project Beta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | cubic yards | square feet | square meters | cubic yards | meters | ls | ls | bags | pounds
| 2024-02-08 | 4: 89.3848
| 2024-02-09 | 1: 21.0325
| 2024-02-12 | 1: 5.5604
| 2024-02-13 | 032: 71.9021
TOTAL |  | 1: 26.5928; 4: 89.3848; 032: 71.9021

## 02-06-24
Pacific Restoration Group, Inc.
555555 Project Beta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | cubic yards | square feet | square meters | cubic yards | meters | ls | ls | bags | pounds
| 2024-02-01 | 2: 192.2433
| 2024-02-02 | 029: 57.0019
| 2024-02-03 | 029: 34.5451; 030: 83.2849
| 2024-02-06 | 029: 56.013
TOTAL |  | 2: 192.2433; 029: 147.56; 030: 83.2849

## 01-30-24
Pacific Restoration Group, Inc.
555555 Project Beta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | cubic yards | square feet | square meters | cubic yards | meters | ls | ls | bags | pounds
| 2024-01-24 | 2: 40.5831
| 2024-01-26 | 029: 149.5573; 031: 171.842
TOTAL |  | 2: 40.5831; 029: 149.5573; 031: 171.842

## 01-23-24
Pacific Restoration Group, Inc.
555555 Project Beta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | cubic yards | square feet | square meters | cubic yards | meters | ls | ls | bags | pounds
| 2024-01-18 | 1: 188.0738; 030: 310.1659; 032: 296.2113
| 2024-01-22 | 2: 385.965
TOTAL |  | 1: 188.0738; 2: 385.965; 030: 310.1659; 032: 296.2113

## 01-16-24
Pacific Restoration Group, Inc.
555555 Project Beta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | cubic yards | square feet | square meters | cubic yards | meters | ls | ls | bags | pounds
| 2024-01-11 | 1: 30.2891; 2: 40.5481; 030: 385.9535; 033: 813.6754
| 2024-01-12 | 2: 887.9988
| 2024-01-14 | 2: 1483.7353; 031: 412.4615
| 2024-01-15 | 2: 183.5501; 030: 394.5437
TOTAL |  | 1: 30.2891; 2: 2595.8324; 030: 780.4972; 031: 412.4615; 033: 813.6754

## 01-09-24
Pacific Restoration Group, Inc.
555555 Project Beta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | cubic yards | square feet | square meters | cubic yards | meters | ls | ls | bags | pounds
| 2024-01-03 | 1: 291.372; 032: 56.8907
| 2024-01-05 | 029: 100.3145
| 2024-01-09 | 4: 379.4067; 5: 33.6752; 031: 59.6297
TOTAL |  | 291.372 |  | 379.4067 | 33.6752 | 100.3145 |  | 59.6297 | 56.8907