## 2024-05-30
Pacific Restoration Group, Inc.
555555 Project Epsilon
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | cubic yards | tons | square meters | pounds | feet | rolls | rolls | gallons | tons
| 2024-05-28 | 2: 848.3159
| 2024-05-29 | 031: 755.7042
| 2024-05-30 | 1: 55.3236; 5: 139.1921
TOTAL |  | 1: 55.3236; 2: 848.3159; 5: 139.1921; 031: 755.7042

## 2024-05-27
Pacific Restoration Group, Inc.
555555 Project Epsilon
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | cubic yards | tons | square meters | pounds | feet | rolls | rolls | gallons | tons
| 2024-05-21 | 1: 137.4934; 4: 591.5185
| 2024-05-23 | 2: 139.5407
| 2024-05-26 | 030: 69.3682
| 2024-05-27 | 5: 6.3096
TOTAL |  | 1: 137.4934; 2: 139.5407; 4: 591.5185; 5: 6.3096; 030: 69.3682

## 2024-05-20
Pacific Restoration Group, Inc.
555555 Project Epsilon
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | cubic yards | tons | square meters | pounds | feet | rolls | rolls | gallons | tons
| 2024-05-14 | 032: 300.5201
| 2024-05-15 | 2: 43.3387; 5: 103.7709; 031: 4.1317
TOTAL |  | 2: 43.3387; 5: 103.7709; 031: 4.1317; 032: 300.5201

## 2024-05-13
Pacific Restoration Group, Inc.
555555 Project Epsilon
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | cubic yards | tons | square meters | pounds | feet | rolls | rolls | gallons | tons
| 2024-05-10 | 4: 82.9128
| 2024-05-13 | 031: 215.6413
TOTAL |  | 4: 82.9128; 031: 215.6413

## 2024-05-06
Pacific Restoration Group, Inc.
555555 Project Epsilon
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | cubic yards | tons | square meters | pounds | feet | rolls | rolls | gallons | tons
| 2024-04-30 | 033: 43.2967
| 2024-05-01 | 5: 143.9544
| 2024-05-03 | 030: 97.4341
| 2024-05-04 | 5: 207.7276
| 2024-05-05 | 029: 266.4724
TOTAL |  | 5: 351.6819; 029: 266.4724; 030: 97.4341; 033: 43.2967

## 2024-04-29
Pacific Restoration Group, Inc.
555555 Project Epsilon
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | cubic yards | tons | square meters | pounds | feet | rolls | rolls | gallons | tons
| 2024-04-25 | 029: 247.1916
| 2024-04-26 | 1: 333.7363
| 2024-04-27 | 2: 169.0942; 029: 903.5334; 033: 8.8182
| 2024-04-28 | 032: 604.8294
| 2024-04-29 | 032: 289.0123
TOTAL |  | 1: 333.7363; 2: 169.0942; 029: 1150.725; 032: 893.8417; 033: 8.8182

## 2024-04-22
Pacific Restoration Group, Inc.
555555 Project Epsilon
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | cubic yards | tons | square meters | pounds | feet | rolls | rolls | gallons | tons
| 2024-04-17 | 030: 304.69
| 2024-04-21 | 2: 835.4547
TOTAL |  | 2: 835.4547; 030: 304.69

## 2024-04-15
Pacific Restoration Group, Inc.
555555 Project Epsilon
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | cubic yards | tons | square meters | pounds | feet | rolls | rolls | gallons | tons
| 2024-04-13 | 5: 133.979
TOTAL |  | 5: 133.979

## 2024-04-08
Pacific Restoration Group, Inc.
555555 Project Epsilon
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | cubic yards | tons | square meters | pounds | feet | rolls | rolls | gallons | tons
| 2024-04-03 | 030: 3.5995
| 2024-04-04 | 2: 424.7317
| 2024-04-05 | 1: 747.8644; 4: 186.5478
| 2024-04-06 | 030: 22.8202
| 2024-04-08 | 2: 22.4977
TOTAL |  | 1: 747.8644; 2: 447.2294; 4: 186.5478; 030: 26.4197

## 2024-04-01
Pacific Restoration Group, Inc.
555555 Project Epsilon
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | cubic yards | tons | square meters | pounds | feet | rolls | rolls | gallons | tons
| 2024-03-26 | 4: 16.4686
| 2024-04-01 | 032: 127.0547; 033: 130.5896
TOTAL |  | 4: 16.4686; 032: 127.0547; 033: 130.5896

## 2024-03-25
Pacific Restoration Group, Inc.
555555 Project Epsilon
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | cubic yards | tons | square meters | pounds | feet | rolls | rolls | gallons | tons
| 2024-03-21 | 032: 371.5253; 033: 104.1815
| 2024-03-22 | 4: 0; 5: 625.6307
| 2024-03-23 | 033: 366.9268
| 2024-03-25 | 4: 62.9427
TOTAL |  | 4: 62.9427; 5: 625.6307; 032: 371.5253; 033: 471.1083

## 2024-03-18
Pacific Restoration Group, Inc.
555555 Project Epsilon
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | cubic yards | tons | square meters | pounds | feet | rolls | rolls | gallons | tons
| 2024-03-12 | 1: 133.6635
| 2024-03-13 | 030: 377.7729
| 2024-03-14 | 5: 707.0594
| 2024-03-15 | 2: 227.3144; 029: 79.8172; 030: 671.3922
| 2024-03-16 | 032: 23.4472
TOTAL |  | 133.6635 | 227.3144 |  | 707.0594 | 79.8172 | 1049.165 |  | 23.4472

## 2024-03-11
Pacific Restoration Group, Inc.
555555 Project Epsilon
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | cubic yards | tons | square meters | pounds | feet | rolls | rolls | gallons | tons
| 2024-03-06 | 1: 300.6739
| 2024-03-11 | 5: 125.3088; 031: 273.1955
TOTAL |  | 1: 300.6739; 5: 125.3088; 031: 273.1955

## 2024-03-04
Pacific Restoration Group, Inc.
555555 Project Epsilon
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | cubic yards | tons | square meters | pounds | feet | rolls | rolls | gallons | tons
| 2024-02-28 | 030: 326.4084; 033: 452.3995
| 2024-03-01 | 5: 117.8952; 031: 27.9785
| 2024-03-03 | 032: 654.9879
TOTAL |  | 5: 117.8952; 030: 326.4084; 031: 27.9785; 032: 654.9879; 033: 452.3995

## 2024-02-26
Pacific Restoration Group, Inc.
555555 Project Epsilon
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | cubic yards | tons | square meters | pounds | feet | rolls | rolls | gallons | tons
| 2024-02-20 | 4: 366.3878
| 2024-02-21 | 031: 698.0223
| 2024-02-22 | 033: 133.9686
| 2024-02-25 | 5: 160.249; 029: 212.0492; 030: 763.9873
| 2024-02-26 | 2: 194.8451; 032: 452.1691
TOTAL |  |  | 194.8451 | 366.3878 | 160.249 | 212.0492 | 763.9873 | 698.0223 | 452.1691 | 133.9686

## 2024-02-19
Pacific Restoration Group, Inc.
555555 Project Epsilon
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | cubic yards | tons | square meters | pounds | feet | rolls | rolls | gallons | tons
| 2024-02-14 | 1: 263.2929
| 2024-02-15 | 5: 365.6003
| 2024-02-16 | 2: 24.4243
TOTAL |  | 1: 263.2929; 2: 24.4243; 5: 365.6003

## 2024-02-12
Pacific Restoration Group, Inc.
555555 Project Epsilon
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | cubic yards | tons | square meters | pounds | feet | rolls | rolls | gallons | tons
| 2024-02-06 | 031: 12.5774
| 2024-02-08 | 4: 425.2581
| 2024-02-09 | 5: 15.5241
| 2024-02-10 | 030: 135.1946
| 2024-02-12 | 2: 51.1546
TOTAL |  | 2: 51.1546; 4: 425.2581; 5: 15.5241; 030: 135.1946; 031: 12.5774

## 2024-02-05
Pacific Restoration Group, Inc.
555555 Project Epsilon
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | cubic yards | tons | square meters | pounds | feet | rolls | rolls | gallons | tons
| 2024-01-30 | 2: 8.4748; 4: 213.2554
| 2024-02-01 | 029: 63.4352
| 2024-02-04 | 1: 190.1155; 031: 250.466
TOTAL |  | 1: 190.1155; 2: 8.4748; 4: 213.2554; 029: 63.4352; 031: 250.466

## 2024-01-29
Pacific Restoration Group, Inc.
555555 Project Epsilon
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | cubic yards | tons | square meters | pounds | feet | rolls | rolls | gallons | tons
| 2024-01-24 | 029: 0.94284
| 2024-01-26 | 030: 141.2663
| 2024-01-27 | 2: 9.926
| 2024-01-29 | 4: 123.5971
TOTAL |  | 2: 9.926; 4: 123.5971; 029: 0.94284; 030: 141.2663

## 2024-01-22
Pacific Restoration Group, Inc.
555555 Project Epsilon
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | cubic yards | tons | square meters | pounds | feet | rolls | rolls | gallons | tons
| 2024-01-18 | 4: 117.8656
| 2024-01-20 | 033: 42.1633
| 2024-01-21 | 5: 6.7416
TOTAL |  | 4: 117.8656; 5: 6.7416; 033: 42.1633

## 2024-01-15
Pacific Restoration Group, Inc.
555555 Project Epsilon
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | cubic yards | tons | square meters | pounds | feet | rolls | rolls | gallons | tons
| 2024-01-10 | 5: 513.551; 029: 810.1195; 032: 770.6673
| 2024-01-14 | 1: 90.1326
TOTAL |  | 1: 90.1326; 5: 513.551; 029: 810.1195; 032: 770.6673

## 2024-01-08
Pacific Restoration Group, Inc.
555555 Project Epsilon
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | cubic yards | tons | square meters | pounds | feet | rolls | rolls | gallons | tons
| 2024-01-02 | 032: 225.0083
| 2024-01-04 | 031: 36.3091
| 2024-01-06 | 030: 119.7337
| 2024-01-07 | 029: 173.1798; 031: 585.9138
| 2024-01-08 | 031: 507.9977
TOTAL |  | 029: 173.1798; 030: 119.7337; 031: 1130.2206; 032: 225.0083