## 05-26-24
Pacific Restoration Group, Inc.
666666 Project Delta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | meters | gallons | gallons | square feet | ls | acres | gallons | tons | cubic yards
| 2024-05-21 | 2: 144.7467
| 2024-05-22 | 031: 47.3535
| 2024-05-23 | 033: 746.0935
| 2024-05-24 | 032: 35.7325
| 2024-05-26 | 1: 350.0391
TOTAL |  | 1: 350.0391; 2: 144.7467; 031: 47.3535; 032: 35.7325; 033: 746.0935

## 05-20-24
Pacific Restoration Group, Inc.
666666 Project Delta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | meters | gallons | gallons | square feet | ls | acres | gallons | tons | cubic yards
| 2024-05-15 | 033: 146.2679
| 2024-05-18 | 314.4349 | 918.9144 |  |  | 107.6206 | 63.4122 | 143.7575 | 312.1736
| 2024-05-20 | 031: 826.3033
TOTAL |  | 314.4349 | 918.9144 |  |  | 107.6206 | 63.4122 | 970.0607 | 312.1736 | 146.2679

## 05-13-24
Pacific Restoration Group, Inc.
666666 Project Delta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | meters | gallons | gallons | square feet | ls | acres | gallons | tons | cubic yards
| 2024-05-10 | 030: 287.5548
TOTAL |  | 030: 287.5548

## 05-06-24
Pacific Restoration Group, Inc.
666666 Project Delta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | meters | gallons | gallons | square feet | ls | acres | gallons | tons | cubic yards
| 2024-04-30 | 2: 142.0816; 4: 450.5998
| 2024-05-02 | 033: 127.2485
| 2024-05-03 | 5: 200.6574; 031: 160.2901
| 2024-05-04 | 2: 58.9329
| 2024-05-05 | 032: 41.9011
TOTAL |  |  | 201.0145 | 450.5998 | 200.6574 |  |  | 160.2901 | 41.9011 | 127.2485

## 04-29-24
Pacific Restoration Group, Inc.
666666 Project Delta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | meters | gallons | gallons | square feet | ls | acres | gallons | tons | cubic yards
| 2024-04-24 | 033: 179.3528
| 2024-04-26 | 1: 409.038
| 2024-04-28 | 1: 98.0338; 4: 249.6025
TOTAL |  | 1: 507.0718; 4: 249.6025; 033: 179.3528

## 04-22-24
Pacific Restoration Group, Inc.
666666 Project Delta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | meters | gallons | gallons | square feet | ls | acres | gallons | tons | cubic yards
| 2024-04-16 | 030: 489.3179; 032: 202.3452; 033: 348.7762
| 2024-04-18 | 4: 52.2728
| 2024-04-19 | 2: 186.9854
| 2024-04-21 | 032: 24.3219
TOTAL |  | 2: 186.9854; 4: 52.2728; 030: 489.3179; 032: 226.6671; 033: 348.7762

## 04-15-24
Pacific Restoration Group, Inc.
666666 Project Delta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | meters | gallons | gallons | square feet | ls | acres | gallons | tons | cubic yards
| 2024-04-09 | 4: 468.4551; 033: 308.4625
| 2024-04-10 | 031: 224.3294
| 2024-04-12 | 032: 290.7908
TOTAL |  | 4: 468.4551; 031: 224.3294; 032: 290.7908; 033: 308.4625

## 04-08-24
Pacific Restoration Group, Inc.
666666 Project Delta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | meters | gallons | gallons | square feet | ls | acres | gallons | tons | cubic yards
| 2024-04-02 | 4: 362.1836; 5: 368.8418
| 2024-04-04 | 031: 321.5825
| 2024-04-05 | 4: 119.6153
| 2024-04-07 | 031: 41.8678
TOTAL |  | 4: 481.7989; 5: 368.8418; 031: 363.4503

## 04-01-24
Pacific Restoration Group, Inc.
666666 Project Delta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | meters | gallons | gallons | square feet | ls | acres | gallons | tons | cubic yards
| 2024-03-26 | 029: 145.3274
| 2024-03-30 | 5: 93.8127; 029: 287.7163
TOTAL |  | 5: 93.8127; 029: 433.0437

## 03-25-24
Pacific Restoration Group, Inc.
666666 Project Delta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | meters | gallons | gallons | square feet | ls | acres | gallons | tons | cubic yards
| 2024-03-20 | 030: 72.3898
TOTAL |  | 030: 72.3898

## 03-18-24
Pacific Restoration Group, Inc.
666666 Project Delta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | meters | gallons | gallons | square feet | ls | acres | gallons | tons | cubic yards
| 2024-03-12 | 1: 389.6988
| 2024-03-14 | 5: 179.5403
| 2024-03-16 | 033: 177.8222
TOTAL |  | 1: 389.6988; 5: 179.5403; 033: 177.8222

## 03-11-24
Pacific Restoration Group, Inc.
666666 Project Delta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | meters | gallons | gallons | square feet | ls | acres | gallons | tons | cubic yards
| 2024-03-05 | 031: 4.4916
| 2024-03-06 | 029: 114.5586; 031: 549.007
| 2024-03-07 | 5: 126.1325; 033: 1.9562
| 2024-03-09 | 5: 546.5225; 032: 61.1518
TOTAL |  | 5: 672.6549; 029: 114.5586; 031: 553.4986; 032: 61.1518; 033: 1.9562

## 03-04-24
Pacific Restoration Group, Inc.
666666 Project Delta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | meters | gallons | gallons | square feet | ls | acres | gallons | tons | cubic yards
| 2024-02-29 | 031: 95.285
| 2024-03-01 | 030: 49.6023
| 2024-03-03 | 029: 666.3158
| 2024-03-04 | 2: 217.9375
TOTAL |  | 2: 217.9375; 029: 666.3158; 030: 49.6023; 031: 95.285

## 02-26-24
Pacific Restoration Group, Inc.
666666 Project Delta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | meters | gallons | gallons | square feet | ls | acres | gallons | tons | cubic yards
| 2024-02-20 | 4: 133.0203; 031: 355.2038; 033: 370.3484
| 2024-02-22 | 4: 192.0389
| 2024-02-23 | 030: 454.7371
| 2024-02-25 | 029: 6.9416
| 2024-02-26 | 031: 181.9706
TOTAL |  | 4: 325.0592; 029: 6.9416; 030: 454.7371; 031: 537.1744; 033: 370.3484

## 02-19-24
Pacific Restoration Group, Inc.
666666 Project Delta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | meters | gallons | gallons | square feet | ls | acres | gallons | tons | cubic yards
| 2024-02-13 | 2: 71.5578
| 2024-02-14 | 2: 57.228
| 2024-02-18 | 4: 96.0997
TOTAL |  | 2: 128.7858; 4: 96.0997

## 02-12-24
Pacific Restoration Group, Inc.
666666 Project Delta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | meters | gallons | gallons | square feet | ls | acres | gallons | tons | cubic yards
| 2024-02-06 | 1: 154.3139
| 2024-02-07 | 031: 30.5315
| 2024-02-10 | 029: 184.6548
| 2024-02-11 | 033: 417.6079
| 2024-02-12 | 031: 499.7872
TOTAL |  | 1: 154.3139; 029: 184.6548; 031: 530.3187; 033: 417.6079

## 02-05-24
Pacific Restoration Group, Inc.
666666 Project Delta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | meters | gallons | gallons | square feet | ls | acres | gallons | tons | cubic yards
| 2024-01-31 | 031: 79.7073
| 2024-02-02 | 030: 220.3367
| 2024-02-04 | 033: 974.0652
TOTAL |  | 030: 220.3367; 031: 79.7073; 033: 974.0652

## 01-29-24
Pacific Restoration Group, Inc.
666666 Project Delta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | meters | gallons | gallons | square feet | ls | acres | gallons | tons | cubic yards
| 2024-01-23 | 1: 71.1149
| 2024-01-26 | 2: 80.8436; 032: 223.577; 033: 417.0964
| 2024-01-28 | 4: 57.8893
TOTAL |  | 1: 71.1149; 2: 80.8436; 4: 57.8893; 032: 223.577; 033: 417.0964

## 01-22-24
Pacific Restoration Group, Inc.
666666 Project Delta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | meters | gallons | gallons | square feet | ls | acres | gallons | tons | cubic yards
| 2024-01-18 | 2: 43.8087
| 2024-01-19 | 1: 3.4979
| 2024-01-20 | 029: 301.659
| 2024-01-22 | 4: 325.8567
TOTAL |  | 1: 3.4979; 2: 43.8087; 4: 325.8567; 029: 301.659

## 01-15-24
Pacific Restoration Group, Inc.
666666 Project Delta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | meters | gallons | gallons | square feet | ls | acres | gallons | tons | cubic yards
| 2024-01-09 | 2: 4.5232
| 2024-01-12 | 4: 351.7487
| 2024-01-14 | 1: 454.0927; 032: 477.4649
| 2024-01-15 | 2: 433.9402; 030: 227.8397
TOTAL |  | 1: 454.0927; 2: 438.4635; 4: 351.7487; 030: 227.8397; 032: 477.4649

## 01-08-24
Pacific Restoration Group, Inc.
666666 Project Delta
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | meters | gallons | gallons | square feet | ls | acres | gallons | tons | cubic yards
| 2024-01-02 | 033: 441.2307
| 2024-01-03 | 4: 47.3222; 5: 698.9368
| 2024-01-04 | 032: 434.1746
| 2024-01-05 | 032: 20.9746
| 2024-01-06 | 030: 23.5025
TOTAL |  | 4: 47.3222; 5: 698.9368; 030: 23.5025; 032: 455.1493; 033: 441.2307