## 05-23-24
Pacific Restoration Group, Inc.
666666 Project Gamma
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | square meters | square feet | tons | pounds | acres | ls | square feet | square meters | cubic yards
| 2024-05-22 | 1: 402.0169
| 2024-05-23 | 1: 224.9028
TOTAL |  | 1: 626.9196

## 05-21-24
Pacific Restoration Group, Inc.
666666 Project Gamma
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | square meters | square feet | tons | pounds | acres | ls | square feet | square meters | cubic yards
| 2024-05-15 | 032: 369.594
| 2024-05-21 | 029: 91.605; 031: 488.7814; 033: 652.8879
TOTAL |  | 029: 91.605; 031: 488.7814; 032: 369.594; 033: 652.8879

## 05-14-24
Pacific Restoration Group, Inc.
666666 Project Gamma
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | square meters | square feet | tons | pounds | acres | ls | square feet | square meters | cubic yards
| 2024-05-08 | 033: 603.3718
| 2024-05-13 | 1: 525.7023; 2: 428.6742
| 2024-05-14 | 2: 116.9217
TOTAL |  | 1: 525.7023; 2: 545.5959; 033: 603.3718

## 05-07-24
Pacific Restoration Group, Inc.
666666 Project Gamma
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | square meters | square feet | tons | pounds | acres | ls | square feet | square meters | cubic yards
| 2024-05-04 | 029: 18.4799
| 2024-05-05 | 4: 703.3569; 030: 142.1561
| 2024-05-06 | 033: 184.5307
| 2024-05-07 | 1: 818.0475
TOTAL |  | 1: 818.0475; 4: 703.3569; 029: 18.4799; 030: 142.1561; 033: 184.5307

## 04-30-24
Pacific Restoration Group, Inc.
666666 Project Gamma
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | square meters | square feet | tons | pounds | acres | ls | square feet | square meters | cubic yards
| 2024-04-24 | 033: 147.3965
| 2024-04-26 | 031: 167.1741; 032: 317.7709
| 2024-04-27 | 033: 170.3505
| 2024-04-29 | 2: 24.3773; 4: 406.5665
| 2024-04-30 | 2: 336.2517
TOTAL |  | 2: 360.629; 4: 406.5665; 031: 167.1741; 032: 317.7709; 033: 317.7471

## 04-23-24
Pacific Restoration Group, Inc.
666666 Project Gamma
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | square meters | square feet | tons | pounds | acres | ls | square feet | square meters | cubic yards
| 2024-04-19 | 030: 37.1749
| 2024-04-20 | 2: 199.7136; 032: 445.9671
| 2024-04-21 | 2: 15.7336
TOTAL |  | 2: 215.4471; 030: 37.1749; 032: 445.9671

## 04-16-24
Pacific Restoration Group, Inc.
666666 Project Gamma
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | square meters | square feet | tons | pounds | acres | ls | square feet | square meters | cubic yards
| 2024-04-10 | 1: 106.426; 033: 444.9243
| 2024-04-11 | 029: 579.1102; 031: 158.6614
| 2024-04-12 | 1: 269.7266
| 2024-04-13 | 030: 467.6105
| 2024-04-14 | 033: 12.1599
TOTAL |  | 1: 376.1527; 029: 579.1102; 030: 467.6105; 031: 158.6614; 033: 457.0842

## 04-09-24
Pacific Restoration Group, Inc.
666666 Project Gamma
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | square meters | square feet | tons | pounds | acres | ls | square feet | square meters | cubic yards
| 2024-04-03 | 030: 15.279
| 2024-04-04 | 5: 264.3127
| 2024-04-06 | 032: 793.3667
| 2024-04-07 | 1: 448.1982; 4: 32.2624
| 2024-04-09 | 030: 183.8383; 032: 412.2363
TOTAL |  | 1: 448.1982; 4: 32.2624; 5: 264.3127; 030: 199.1173; 032: 1205.603

## 04-02-24
Pacific Restoration Group, Inc.
666666 Project Gamma
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | square meters | square feet | tons | pounds | acres | ls | square feet | square meters | cubic yards
| 2024-03-27 | 2: 375.5436; 030: 351.1325
| 2024-03-31 | 1: 661.9293
| 2024-04-01 | 5: 33.5124; 029: 155.9475
| 2024-04-02 | 032: 97.6601
TOTAL |  | 661.9293 | 375.5436 |  | 33.5124 | 155.9475 | 351.1325 |  | 97.6601

## 03-26-24
Pacific Restoration Group, Inc.
666666 Project Gamma
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | square meters | square feet | tons | pounds | acres | ls | square feet | square meters | cubic yards
| 2024-03-20 | 033: 9.8471
| 2024-03-21 | 029: 95.1946
| 2024-03-23 | 1: 24.1274
| 2024-03-24 | 030: 98.4656
TOTAL |  | 1: 24.1274; 029: 95.1946; 030: 98.4656; 033: 9.8471

## 03-19-24
Pacific Restoration Group, Inc.
666666 Project Gamma
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | square meters | square feet | tons | pounds | acres | ls | square feet | square meters | cubic yards
| 2024-03-13 | 1: 47.796; 5: 187.1939
| 2024-03-14 | 031: 841.0887
| 2024-03-16 | 1: 41.8482
| 2024-03-18 | 032: 23.212
TOTAL |  | 1: 89.6442; 5: 187.1939; 031: 841.0887; 032: 23.212

## 03-12-24
Pacific Restoration Group, Inc.
666666 Project Gamma
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | square meters | square feet | tons | pounds | acres | ls | square feet | square meters | cubic yards
| 2024-03-07 | 029: 136.032
| 2024-03-09 | 2: 316.5743
| 2024-03-11 | 4: 400.4761
| 2024-03-12 | 4: 321.62
TOTAL |  | 2: 316.5743; 4: 722.0961; 029: 136.032

## 03-05-24
Pacific Restoration Group, Inc.
666666 Project Gamma
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | square meters | square feet | tons | pounds | acres | ls | square feet | square meters | cubic yards
| 2024-03-01 | 4: 24.6325
| 2024-03-02 | 1: 12.0293; 032: 119.5187
| 2024-03-03 | 2: 17.1241; 5: 140.4433
| 2024-03-04 | 4: 217.2473
TOTAL |  | 1: 12.0293; 2: 17.1241; 4: 241.8798; 5: 140.4433; 032: 119.5187

## 02-27-24
Pacific Restoration Group, Inc.
666666 Project Gamma
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | square meters | square feet | tons | pounds | acres | ls | square feet | square meters | cubic yards
| 2024-02-22 | 032: 386.1562
| 2024-02-23 | 029: 28.0206
| 2024-02-27 | 4: 747.5981
TOTAL |  | 4: 747.5981; 029: 28.0206; 032: 386.1562

## 02-20-24
Pacific Restoration Group, Inc.
666666 Project Gamma
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | square meters | square feet | tons | pounds | acres | ls | square feet | square meters | cubic yards
| 2024-02-14 | 032: 512.276
| 2024-02-17 | 5: 196.8591; 033: 157.6913
| 2024-02-18 | 029: 63.4409; 030: 717.5594; 033: 784.1386
TOTAL |  | 5: 196.8591; 029: 63.4409; 030: 717.5594; 032: 512.276; 033: 941.8299

## 02-13-24
Pacific Restoration Group, Inc.
666666 Project Gamma
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | square meters | square feet | tons | pounds | acres | ls | square feet | square meters | cubic yards
| 2024-02-10 | 030: 39.0396
| 2024-02-11 | 2: 322.4705; 031: 400.6144
TOTAL |  | 2: 322.4705; 030: 39.0396; 031: 400.6144

## 02-06-24
Pacific Restoration Group, Inc.
666666 Project Gamma
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | square meters | square feet | tons | pounds | acres | ls | square feet | square meters | cubic yards
| 2024-01-31 | 030: 373.9663
| 2024-02-01 | 5: 39.2503
| 2024-02-03 | 1: 232.5124
| 2024-02-04 | 5: 17.8965; 029: 257.1456
| 2024-02-05 | 5: 316.2798
TOTAL |  | 1: 232.5124; 5: 373.4266; 029: 257.1456; 030: 373.9663

## 01-30-24
Pacific Restoration Group, Inc.
666666 Project Gamma
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | square meters | square feet | tons | pounds | acres | ls | square feet | square meters | cubic yards
| 2024-01-26 | 033: 3.6504
| 2024-01-28 | 031: 416.5307
| 2024-01-29 | 029: 1.6482; 030: 13.6353
TOTAL |  | 029: 1.6482; 030: 13.6353; 031: 416.5307; 033: 3.6504

## 01-23-24
Pacific Restoration Group, Inc.
666666 Project Gamma
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | square meters | square feet | tons | pounds | acres | ls | square feet | square meters | cubic yards
| 2024-01-18 | 033: 249.8883
| 2024-01-22 | 032: 73.7974
| 2024-01-23 | 1: 327.7891
TOTAL |  | 1: 327.7891; 032: 73.7974; 033: 249.8883

## 01-16-24
Pacific Restoration Group, Inc.
666666 Project Gamma
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | square meters | square feet | tons | pounds | acres | ls | square feet | square meters | cubic yards
| 2024-01-16 | 029: 245.7691
TOTAL |  | 029: 245.7691

## 01-09-24
Pacific Restoration Group, Inc.
666666 Project Gamma
| Bid Item | 1 | 2 | 4 | 5 | 029 | 030 | 031 | 032 | 033
|  | Hydroseed | Hydromulch | Fiber-rolls | Sprinkler | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm | Temp Gravel Bag Berm
| Date | square meters | square feet | tons | pounds | acres | ls | square feet | square meters | cubic yards
| 2024-01-03 | 032: 110.3025
| 2024-01-04 | 029: 208.8621
| 2024-01-07 | 1: 1.9581; 2: 141.5249; 030: 381.9705
| 2024-01-09 | 1: 11.847; 2: 406.7625
TOTAL |  | 1: 13.8051; 2: 548.2874; 029: 208.8621; 030: 381.9705; 032: 110.3025