## ProgressSheet
Pacific Restoration Group, Inc.
555555 Project Epsilon
| Bid Item | 1 | 10 | 11 | 12 | 13 | 2 | 4 | 5 | 6 | 7 | 8 | 9
|  | Hydroseed | Fiberrolls | Fiberrolls | Fiberrolls | Fiberrolls | Hydromulch | Fiberrolls | Sprinkler | Pipe | Gravel | Fiberrolls | Fiberrolls
| Date | bags | meters | acres | cubic yards | pounds | meters | meters | rolls | square meters | bags | pounds | ls
Jan 01 - Jan 21
| 2024-01-01 | 5: 393.8968
| 2024-01-03 | 11: 267.571
| 2024-01-12 | 4: 70.5055
| 2024-01-21 | 11: 423.0454; 6: 330.2758
Jan 22 - Feb 21
| 2024-01-22 | 11: 445.717
| 2024-01-24 | 13: 168.8724
| 2024-01-25 | 8: 102.3827
| 2024-01-26 | 1: 178.2159
| 2024-02-01 | 1: 358.0428; 9: 53.6803
| 2024-02-02 | 11: 12.0062; 8: 71.5536; 9: 8.1089
| 2024-02-03 | 12: 202.5469; 7: 326.6321
| 2024-02-05 | 12: 576.9855
| 2024-02-06 | 6: 162.603; 7: 740.205
| 2024-02-07 | 8: 35.3132
| 2024-02-10 | 10: 280.583; 8: 231.0729
| 2024-02-12 | 6: 801.7251
| 2024-02-13 | 9: 240.709
| 2024-02-14 | 11: 10.1198; 13: 449.6716
| 2024-02-15 | 8: 527.0036
| 2024-02-16 | 5: 267.0191
| 2024-02-17 | 6: 232.3527; 8: 357.8831
| 2024-02-19 | 9: 135.0283
| 2024-02-20 | 7: 47.6046
| 2024-02-21 | 8: 289.7659
Feb 22 - Mar 21
| 2024-02-22 | 10: 27.1549
| 2024-02-23 | 13: 13.6805
| 2024-02-24 | 6: 103.0904
| 2024-02-26 | 12: 463.1005; 4: 371.485
| 2024-02-27 | 1: 399.2659
| 2024-02-29 | 11: 406.8808
| 2024-03-02 | 12: 165.2064
| 2024-03-03 | 13: 838.6243
| 2024-03-05 | 5: 226.2589
| 2024-03-06 | 13: 32.2557; 6: 318.9298
| 2024-03-09 | 2: 261.5176; 4: 325.1723
| 2024-03-10 | 1: 428.2866
| 2024-03-15 | 9: 627.4864
| 2024-03-16 | 4: 184.329
| 2024-03-18 | 2: 37.1875
Mar 22 - Apr 21
| 2024-03-26 | 1: 296.6536; 10: 389.0019
| 2024-03-28 | 11: 44.7549; 4: 56.3912
| 2024-03-29 | 7: 178.3737
| 2024-03-31 | 8: 845.378
| 2024-04-02 | 11: 120.7232; 13: 316.0486; 6: 66.236
| 2024-04-05 | 9: 336.1092
| 2024-04-07 | 10: 61.4736; 13: 65.6597
| 2024-04-10 | 6: 860.2304
| 2024-04-13 | 11: 325.127; 12: 357.1787
| 2024-04-14 | 4: 300.0918; 6: 383.7031; 9: 174.4746
| 2024-04-16 | 13: 339.3605; 4: 249.3121
| 2024-04-19 | 7: 72.2427
| 2024-04-20 | 5: 500.47; 6: 258.0954
Apr 22 - May 21
| 2024-04-24 | 8: 119.369
| 2024-04-25 | 6: 72.0042
| 2024-04-26 | 9: 665.9816
| 2024-04-27 | 12: 149.9107; 6: 70.2807; 9: 286.3677
| 2024-05-03 | 11: 313.0132
| 2024-05-05 | 8: 180.3676
| 2024-05-07 | 5: 254.9346; 6: 25.5579; 9: 224.5533
| 2024-05-10 | 12: 608.0396
| 2024-05-13 | 7: 45.7385
| 2024-05-16 | 1: 49.1887
| 2024-05-17 | 1: 121.3031
| 2024-05-18 | 5: 209.6295
| 2024-05-19 | 7: 105.2306
May 22 - May 30
| 2024-05-22 | 2: 122.0983
| 2024-05-24 | 11: 80.1289; 2: 60.6704
| 2024-05-25 | 10: 145.1456
| 2024-05-28 | 7: 939.0915
| 2024-05-30 | 8: 419.6088