## ProgressSheet
Pacific Restoration Group, Inc.
666666 Project Epsilon
| Bid Item | 1 | 10 | 11 | 12 | 13 | 2 | 4 | 5 | 6 | 7 | 8 | 9
|  | Hydroseed | Fiberrolls | Fiberrolls | Fiberrolls | Fiberrolls | Hydromulch | Fiberrolls | Sprinkler | Pipe | Gravel | Fiberrolls | Fiberrolls
| Date | square feet | feet | acres | cubic yards | acres | bags | bags | square meters | acres | ls | square feet | feet
Feb 09 - Feb 21
| 2024-02-09 | 7: 518.2726
Feb 22 - Mar 21
| 2024-03-15 | 10: 105.8745; 11: 323.6354
Mar 22 - Apr 21
| 2024-04-05 | 1: 528.2962
| 2024-04-07 | 1: 70.0299
| 2024-04-09 | 7: 112.5371
| 2024-04-15 | 6: 224.7615
| 2024-04-16 | 7: 142.9494
| 2024-04-18 | 8: 71.4294
Apr 22 - May 21
| 2024-04-28 | 6: 198.9802
| 2024-04-29 | 2: 53.3682
| 2024-05-01 | 6: 308.5827
| 2024-05-06 | 2: 125.4833
| 2024-05-09 | 1: 184.1645; 7: 0.067628
| 2024-05-12 | 4: 413.7738
| 2024-05-18 | 5: 25.0656
May 22 - Jun 21
| 2024-05-25 | 11: 98.5369
| 2024-06-19 | 12: 237.8267
Jun 22 - Jul 21
| 2024-07-11 | 9: 299.0676
| 2024-07-15 | 9: 611.639
Jul 22 - Aug 21
| 2024-07-22 | 12: 401.2717
| 2024-07-31 | 11: 291.5577
| 2024-08-03 | 12: 484.8476
| 2024-08-11 | 13: 502.714
| 2024-08-17 | 7: 362.582
Aug 22 - Sep 21
| 2024-08-25 | 12: 470.6699
| 2024-09-03 | 9: 343.6893
| 2024-09-04 | 13: 427.1825
| 2024-09-16 | 7: 36.8371; 8: 137.3127
| 2024-09-18 | 1: 234.9325; 8: 104.4364
| 2024-09-19 | 10: 147.0801
Sep 22 - Oct 21
| 2024-10-03 | 13: 59.0222
| 2024-10-09 | 11: 91.9842
| 2024-10-14 | 10: 8.9569; 2: 135.3865
Oct 22 - Nov 21
| 2024-10-28 | 6: 74.1552
Nov 22 - Dec 21
| 2024-12-04 | 4: 606.4317
| 2024-12-07 | 10: 103.3147; 9: 62.3621
| 2024-12-14 | 10: 654.3775
Dec 22 - Jan 21
| 2024-12-22 | 13: 164.9511
| 2025-01-02 | 2: 56.9421
| 2025-01-14 | 12: 201.8924
Jan 22 - Feb 21
| 2025-02-01 | 13: 327.3123
| 2025-02-02 | 9: 468.2069
| 2025-02-03 | 12: 92.8509
Feb 22 - Mar 21
| 2025-03-09 | 6: 52.3184
| 2025-03-21 | 13: 818.752
Mar 22 - Apr 21
| 2025-03-27 | 1: 751.086
| 2025-04-12 | 1: 420.0242
| 2025-04-13 | 6: 113.6917
| 2025-04-17 | 10: 191.5339
| 2025-04-18 | 8: 7.3786
Apr 22 - May 21
| 2025-04-26 | 9: 21.2516
| 2025-05-13 | 4: 289.6161
May 22 - Jun 21
| 2025-05-31 | 12: 499.6565
Jun 22 - Jul 21
| 2025-06-24 | 12: 395.7285
| 2025-07-03 | 6: 183.9559
| 2025-07-21 | 6: 39.8471
Jul 22 - Aug 21
| 2025-07-29 | 6: 220.573
| 2025-07-30 | 7: 173.3991
| 2025-08-02 | 1: 288.3375
| 2025-08-04 | 12: 2.5519
| 2025-08-05 | 9: 712.1786
| 2025-08-11 | 6: 568.0299; 8: 247.0248
| 2025-08-13 | 13: 22.9696
| 2025-08-21 | 11: 787.7201
Aug 22 - Sep 21
| 2025-08-27 | 9: 703.5325
| 2025-09-07 | 1: 258.3851
| 2025-09-10 | 11: 293.1747
| 2025-09-11 | 1: 515.3532
| 2025-09-17 | 2: 320.2986
Sep 22 - Oct 21
| 2025-09-24 | 1: 300.0168
| 2025-09-29 | 12: 29.9755
| 2025-10-04 | 8: 11.3483
| 2025-10-17 | 6: 96.3699
Oct 22 - Nov 21
| 2025-10-22 | 11: 682.5293; 5: 210.1367
| 2025-10-23 | 9: 62.4256
| 2025-10-24 | 5: 529.2896
| 2025-10-25 | 12: 289.2396
| 2025-11-02 | 7: 301.0866
| 2025-11-03 | 1: 163.9939
Nov 22 - Dec 21
| 2025-11-25 | 9: 10.2585
| 2025-11-29 | 4: 460.7098
| 2025-11-30 | 5: 85.4009
| 2025-12-01 | 4: 260.4817
| 2025-12-03 | 10: 510.1018; 7: 5.9485
| 2025-12-08 | 13: 15.6386
| 2025-12-10 | 6: 795.8447
| 2025-12-12 | 4: 526.5393
| 2025-12-15 | 12: 975.0408
Dec 22 - Dec 29
| 2025-12-29 | 12: 172.9006; 5: 258.8444